## FED (hidden)
[7 empty] | Sprints | FED | [6 empty] | Comments
[8 empty] | Manual test case Total | Planned Target(%) | Actual Target(%) | Test cases Automated | Defect Found in Automation | Planned Hours to complete | Actual Hours Taken to complete
[7 empty] | Sprint-1 | 6 | 50 | 100 | 6
[7 empty] | Sprint-2 | 6 | 50 | 67 | 4
[7 empty] | Sprint-3 | 9 | 50 | 100 | 9
[7 empty] | Sprint-4 | 16 | 50 | 13 | 2
[7 empty] | TOTAL | 37 | 50 | 70 | 21
Sprint | User Story Id | Manual Test Case Name | Test Case Description | Automated | Automation Script Name | Comments
Sprint-1 | TFS423 | Title Text_UI | Verify whether the titles are available for H1 through H6 styles on any page | Y | WT_FED_SPRINT1_TFS423_TC_01
Sprint-1 | TFS422 | Basic Text_UI | Verify whether the basic text is displayed | Y | WT_FED_SPRINT1_TFS422_TC_02
Sprint-1 | TFS413 | List_UI | Verify if the list items are displayed in a grouped manner | Y | WT_FED_SPRINT1_TFS413_TC_03
Sprint-1 | TFS411 | Image | Verify whether the image is displayed on the page | Y | WT_FED_SPRINT1_TFS411_TC_04
Sprint-1 | TFS410 | Global header | Verify the global header on every page | Y | WT_FED_SPRINT1_TFS410_TC_05
Sprint-1 | TFS403 | Content_UI | Verify the content is displayed in accordian | Y | WT_FED_SPRINT1_TFS403_TC_06
Sprint-2 | TFS412 | Mobile_First_TFS412_TC_001 | Verify whether the interstitial page is displayed if the user leaves the site through an external link | Y | WT_FED_SPRINT2_TFS412_TC_001
Sprint-2 | TFS407 | Mobile_First_TFS407_TC_001 | Verify whether an external user is able to view a disclaimer | Y | WT_FED_SPRINT2_TFS407_TC_001
Sprint-2 | TFS406 | Mobile_First_TFS406_TC_001 | Verify whether external user is able to view a call to action | Y | WT_FED_SPRINT2_TFS406_TC_001
Sprint-2 | TFS504 | Mobile_First_TFS504_TC_001 | Verify the content displayed in a modal window | Y | WT_FED_SPRINT2_TFS504_TC_001
Sprint-2 | TFS424 | Mobile_First_TFS424_TC_001 | Verify whether the video plays | Not Automatable
Sprint-2 | TFS414 | Mobile_First_TFS414_TC_001 | Verify whether the global navigation is displayed on the site | N
Sprint-3 | TFS624 | As a Front End Developer, I need to develop a button set element so that the end user has the ability to navigate between any of the different options given. | Verify whether the Front End Developer is able to develop a button set element so that the end user has the ability to navigate between any of the different options given. | Y | WT_FED_SPRINT3_TFS634
Sprint-3 | TFS625 | As a Front End Developer, I need to develop an account card element so that the end user has the ability to quickly view basic information about their current car. | Verify whether the front end developer is able to develop an account card element so that the end user has the ability to quickly view basic information about their current car | Y | WT_FED_SPRINT3_TFS625
Sprint-3 | TFS626 | As a Front End Developer, I need to develop a Border Card Variant element. | Verify whether the Front End Developer is able to develop a Border Card Variant element. | Y | WT_FED_SPRINT3_TFS626
Sprint-3 | TFS-629 | As a Front End Developer, I need to develop N up element. | Verify whether theblocks are displayed in 2-up, 3-up or 4-up style. | Y | WT_FED_SPRINT3_TFS629
Sprint-3 | TFS632 | As a Front End Developer, I need to develop Inputs Radio element so that the end user can choose from list of options. | Verify whether the Front End Developer is able to develop Inputs Radio element so that the end user can choose from list of options. | Y | WT_FED_SPRINT3_TFS632
Sprint-3 | TFS-633 | As a Front End Developer, I need to develop Inputs Select element so that the end user can choose from list of options. | Verify whether the end user is able to choose an option from the select element | Y | WT_FED_SPRINT3_TFS633
Sprint-3 | TFS-634 | As a Front End Developer, I need to develop Input Text element so that the end user can enter text. | Verify whether the end user is able to enter a text in the text element | Y | WT_FED_SPRINT3_TFS634
Sprint-3 | TFS-635 | As a Front End Developer, I need to develop Input Checkbox element so that the end user can choose from list of options. | Verify whether the end user can choose from a list of options in a checkbox element. | Y | WT_FED_SPRINT3_TFS635
Sprint-3 | TFS637 | As a Front End Developer, I need to develop a Primary Conversation Layout. | Verify whether the Front End Developer is able to develop a Primary Conversation Layout. | Y | WT_FED_SPRINT3_TFS637
Sprint-4 | TFS409 | FED Component: Footer | Verify the FED Component: Footer | Y | WT_FED_SPRINT4_TFS409
Sprint-4 | TFS420 | As an external user, I need to be able to view a sitemap. | Verify whether the external user is able to view a sitemap. | Y | WT_FED_SPRINT4_TFS420
Sprint-4 | TFS702 | As a Front End Developer, I want to demonstrate flow states for a back end developer to integrate | Verify whether the Front End Developer is able to demonstrate flow states for a back end developer to integra
Sprint-4 | TFS639 | As a Front End Developer, I need to develop a Flow End Layout. | Verify whether the flow end layout is displayed | Not Automatable
Sprint-4 | TFS638 | As a Front End Developer, I need to develop a Decision Layout. | Verify whether the decision layout is displayed | Not Automatable
Sprint-4 | TFS636 | As a Front End Developer, I need to develop a Greeting Layout. | Verify whether the greeting layout is displayed | Not Automatable
Sprint-4 | TFS631 | As a Front End Developer, I need to develop Lite Variant Line Rule. | Verify whether the Lite variant line element is displayed
Sprint-4 | TFS628 | As a Front End Developer, I need to develop a Footnotes element so that notes can be viewed by a user. | Verify whether the footnote is displayed
Sprint-4 | TFS623 | As a Front End Developer, I need to develop a Mobility Mentor element so that the end user has the ability to navigate to a Mobility Mentor message. | Verify whether an end user is able to navigate to the next screen by clicking Mobility mentor element
Sprint-4 | TFS622 | As a Front End Developer, I need to develop a greeting element so that the end user has the ability to navigate to the next screen. | Verify whether the end user is able to navigate to the next screen by clicking Greeting element
Sprint-4 | TFS630_TC001 | As a Front End Developer, I need to develop Editable Card element._TC_001 | Verify whether a card element is editable
Sprint-4 | TFS630_TC002 | As a Front End Developer, I need to develop Editable Card element._TC_002 | Verify whether a card element is static
Sprint-4 | TFS670 | FED Component: Breadcrumbs | Verify the FED Component: Breadcrumbs
Sprint-4 | TFS671 | FED Component: Layout - Interior Page Header | Verify FED Component: Layout - Interior Page Header
Sprint-4 | TFS667 | FED Component: Text Variant - Centered Mobile View | Verify FED Component: Text Variant is left aligned
Sprint-4 | TFS673 | FED Component: Layout - Full Width | Verify FED Component: Layout - Full Width

## DSR-Team
Date | Resources | Description | Script Developed | Executed and Debugged | Issues
2017-12-18 | Palani | Component and Script Development for user Story 810, 816 | 2
2017-12-19 | Palani | Component and Script Development for user Story 817, 826 | 2
2017-12-20 | Palani | Component and Script Development for user Story 827,828 | 3
2017-12-21 | Palani | Component and Script Development for user Story 832,836 | 6
2017-12-22 | Palani | Component and Script Development for user Story 837,839 | 2
2017-12-25 | Palani | Component and Script Development for user Story 867, 865 | 3
2017-12-26 | Palani | Component and Script Development for user Story 868,872 | 3
2017-12-27 | Palani | Component and Script Development for user Story 868,872 | 5
2017-12-03 | Palani | Component and Script Development for user Story 868,872 | 2
2017-12-04 | Palani | Component and Script Development for user Story 840 | 3

## Manual TestCases
Sprint | User Story Id | Manual Test Case Name | Test Case Description | Automated | Automation Script Name | Total No Steps | Complexity | Estimated Hours | Actual Hours Spent | Person Responsible | Start Date | End Date | Comments
1 | CMF - 810 | As an external user, I want to see logo of Toyota Financial Services. | Verify the "Lease Vehicle Purchase Estimator" page in default state. | Not Automatable | CW_User_Story_810_01 | 3 | Simple | 3
1 | CMF - 810 | As an external user, I want to see logo of Toyota Financial Services. | Verify the navigation icon | Y | CW_User_Story_810_02 | 3 | Simple | 3
1 | CMF - 816 | As an external user, I want access to global navigation (Menu) | Verify the Finance term drop down menu | Y | CW_User_Story_816_01 | 6 | Medium | 4
1 | CMF - 834 | As an external user, I want to understand my Financing Options so that I can make an informed decision when purchasing a car. | Verify the Desired APR% field | Functionality Not Yet Developed | CW_User_Story_834_01 | 10 | Complex | 8 |  |  |  |  | N/A- Find a Rebate and Finance program is not delivered as part of sprint 1
1 | CMF - 837 | Verify whether the user is able to access the all the options in Understanding credit of "Financing Options" | Verify whether a Current Lease Customer is able to view the estimated purchase price of the leased vehicle | Y | CW_User_Story_837_01 | 6 | Medium | 4 |  |  |  |  | This case is passed by ignoring alignment Issue in bread crumb
1 | CMF - 837 | Verify when the user click on "Credit 101" page | Verify whether a Current Lease Customer is navigate to the email address verification page when the user clicks on "Skip" button | Y | CW_User_Story_837_02 | 2 | Medium | 4
1 | CMF - 837 | Verify when the user click on "Your Credit" page | Verify whether the Current Lease Customer with multiple accounts is able to view a list of all his lease accounts so that he can select a specific lease account | Y | CW_User_Story_837_03 | 3 | Medium | 4
1 | CMF - 837 | Verify when the user click on "Credit Tips" page | As a current lease customer with multiple accounts, I want to view a list of all of my lease accounts so that I can select a specific lease account | Y | CW_User_Story_837_04 | 3 | Medium | 4
1 | CMF - 837 | Verify whether the all the links under Financing Options navigates to the corresponding page | As an end of term lease customer (< 61 days), I want the system to prompt me so that I can schedule an inspection for my leased vehicle | Y | CW_User_Story_837_05 | 11 | Complex | 8
1 | CMF - 865 | Verify whether the user is able to access the Credit application in "For Business" | Verify the "No" button functionality in the inspection page | Not Automatable | CW_User_Story_865_01 | 5 | Medium | 4
1 | CMF - 865 | Verify whether the user is able to have an overview of all the For Business Links | Verify the "I'm not sure" button functionality in the inspection page | Not Automatable | CW_User_Story_865_02 | 5 | Medium | 4
1 | CMF - 868 | Verify whether the user is able to access the About Us page | Verify when the user clicks "I'm not sure" in the lease end options page | Y | CW_User_Story_868_01 | 4 | Medium | 4
1 | CMF - 868 | Verify whether the user is able to access the Diversity at Toyota | Verify the "Lease end overview page" | Y | CW_User_Story_868_02 | 5 | Medium | 4
1 | CMF - 868 | Verify whether the user is able to access the Preservation | Verify the financing page | Y | CW_User_Story_868_03 | 5 | Medium | 4
1 | CMF - 868 | Verify whether the user is able to access the Community Care | Verify when the user clicks 'Yes' in Financing page | Y | CW_User_Story_868_04 | 5 | Medium | 4
1 | CMF - 868 | Verify whether the all the links under About Us navigates to the corresponding page | Verify when the user clicks 'I'm not sure' in Financing page | Y | CW_User_Story_868_05 | 14 | Complex | 8
1 | CMF - 868 | Verify when the user clicks on "Continue" in the pop-up for redirecting to the external site | Verify the "Lease Vehicle Purchase Estimator" page in default state. | Functionality Not Yet Developed | CW_User_Story_868_06 | 3 | Simple | 3 |  |  |  |  | N/A- pop-up functionality is not yet develeoped
1 | CMF - 868 | Verify when the user clicks on "Return" in the pop-up for redirecting to the external site | Verify the "Lease end purchase" for a current lease customer who has less than 90 days remaining on lease | Functionality Not Yet Developed | CW_User_Story_868_07 | 3 | Simple | 3 |  |  |  |  | N/A- pop-up functionality is not yet develeoped
1 | CMF - 873 | Verify whether the user is able to access the Fair Lending Policies on Click of Continue | Verify whether the system prompts the customer to update his mailing address and the customer clicks on update button | Functionality Not Yet Developed | CW_User_Story_873_01 | 4 | Medium | 4 |  |  |  |  | N/A- pop-up functionality is not yet develeoped
1 | CMF - 873 | Verify when the user clicks on "Return" in the pop-up for redirecting to the external site | Verify whether a Current Lease Customer is navigate to the email address verification page when the user clicks on "Skip" button | Functionality Not Yet Developed | CW_User_Story_873_02 | 4 | Medium | 4 |  |  |  |  | N/A- pop-up functionality is not yet developed
1 | CMF - 840 | Verify whether the user is able to access the Credit Tips Page | Verify the input address field | Y | CW_User_Story_840_01 | 7 | Medium | 4
1 | CMF - 840 | Verify when the user clicks on "Return" in the pop-up for redirecting to the external site | Verify the "City" input field | Yet To Automate | CW_User_Story_840_02 | 3 | Medium | 4
1 | CMF - 840 | Verify when the user clicks on "Continue" in the pop-up for redirecting to the external site | As a customer, I want the system to prompt me to verify my mailing address when appropriate so I can ensure my mailing address is accurate | Yet To Automate | CW_User_Story_840_03 | 3 | Medium | 4
1 | CMF - 840 | Verify whether the all the links under Understanding credit navigates to the corresponding page | Verify whether the system prompts the customer to update his mailing address and the customer clicks on update button | Y | CW_User_Story_840_04 | 9 | Complex | 8
1 | CMF - 840 | Verify whether the all the links under Financing Options navigates to the corresponding page | Verify the input address field | Y | CW_User_Story_840_05 | 11 | Complex | 8
1 | CMF - 865 | Verify whether the user is able to access the Credit application in "For Business" | Verify the "City" input field | Not Automatable | CW_User_Story_865_01 | 5 | Medium | 4
1 | CMF - 865 | Verify whether the user is able to have an overview of all the For Business Links | Verify the "Zip code" input field | Not Automatable | CW_User_Story_865_02 | 5 | Medium | 4
1 | CMF - 865 | Verify whether the all the links under Financing Options navigates to the corresponding page | Verify whether the system prompts the customer to update his mailing address and the customer clicks on cancel button | Y | CW_User_Story_865_03 | 11 | Complex | 8
1 | CMF - 865 | Verify whether the all the links under For Business navigates to the corresponding page | As a current lease customer, I want the system to guide me through the lease end process so I can return my leased vehicle | Y | CW_User_Story_865_04 | 8 | Medium | 4
1 | CMF - 873 | Verify whether the user is able to access the Fair Lending Policies on Click of Continue | Verify the "zip code" in the dealer contact page | Functionality Not Yet Developed | CW_User_Story_873_01 | 4 | Medium | 4 |  |  |  |  | N/A- pop-up functionality is not yet developed
1 | CMF - 873 | Verify when the user clicks on "Return" in the pop-up for redirecting to the external site | Verify the radio buttons in the dealer contact page | Functionality Not Yet Developed | CW_User_Story_873_02 | 4 | Medium | 4 |  |  |  |  | N/A- pop-up functionality is not yet developed
1 | CMF - 817 | As an external user, I want header to be consistent on top while scrolling through the page. | Verify the disclaimer in the dealer contact page | Y | CW_User_Story_817_01 | 5 | Medium | 4
1 | CMF - 819 | Verify whether the user is able to access the various shopping tools provided by TFS | As a current lease customer, I want to understand how to purchase my leased vehicle at the end of my agreement (functional) | Not Automatable | CW_User_Story_819_01 | 6 | Medium | 4
1 | CMF - 819 | Verify whether the user is able to access the various shopping tools provided by TFS when the links are not redirecting to the external site | Verify when the user clicks "purchase it" in the lease end options page | Functionality Not Yet Developed | CW_User_Story_819_02 | 7 | Medium | 4 |  |  |  |  | N/A- pop-up functionality is not yet developed
1 | CMF - 819 | Verify whether the user is able to access the various shopping tools provided by TFS when the links are redirecting to the external site | Verify when the user clicks "I'm not sure" in the lease end options page | Functionality Not Yet Developed | CW_User_Story_819_03 | 7 | Medium | 4 |  |  |  |  | N/A- pop-up functionality is not yet developed
1 | CMF - 820 | Verify whether the user is able to explore various options available for Customer support | Verify when the user clicks "Purchase vehicle" in the lease end overview page | Not Automatable | CW_User_Story_820_01 | 8 | Medium | 4
1 | CMF - 828 | Verify whether the user is able to view information about frequently asked questions | Verify the financing page | Y | CW_User_Story_828_01 | 5 | Medium | 4
1 | CMF - 828 | Verify whether the user is able to view the breadcrumb in FAQ's Page | Verify when the user clicks 'Yes' in Financing page | Y | CW_User_Story_828_02 | 5 | Medium | 4
1 | CMF - 828 | Verify whether the user is able to navigate to various categories of FAQ's | Verify when the user clicks 'I'm not sure' in Financing page | Not Automatable | CW_User_Story_828_03 | 6 | Medium | 4
1 | CMF - 836 | Verify whether the user is able to view the following options in the Leasing a Toyota Vehicle page 1. Global header 2. Global Header Footer. 3. Breadcrumbs. | Verify the "Lease Vehicle Purchase Estimator" page in default state. | Y | CW_User_Story_836_01 | 6 | Medium | 4
1 | CMF - 836 | Verify whether the user is able to view the Financing Options heading on the right side in the leasing a Toyota Vehicle page | Verify the "Lease end purchase" for a current lease customer who has more than 90 days remaining on lease | Y | CW_User_Story_836_02 | 5 | Medium | 4 |  |  |  |  | N/A- Rebate and Finance Program is not delivered as part of sprint 1
1 | CMF - 836 | Verify whether the user is able to view and click the "Excess Wear & Use Protection Plan" text in the leasing a Toyota Vehicle page | Verify the "Lease end purchase" for a current lease customer who has less than 90 days remaining on lease | Functionality Not Yet Developed | CW_User_Story_836_03 | 6 | Medium | 4 |  |  |  |  | N/A- Excess Wear & Use Protection Plan" is not delivered as part of sprint 1
1 | CMF - 836 | Verify whether the user is able to view the Quiz for Buy Vs Lease button in the leasing a Toyota Vehicle page | Verify whether the system prompts the customer to update his mailing address and the customer clicks on update button | Functionality Not Yet Developed | CW_User_Story_836_04 | 6 | Medium | 4 |  |  |  |  | N/A- Quiz is not delivered as part of sprint 1
1 | CMF - 836 | Verify whether the user is able to view the options under Finance Programs in the leasing a Toyota Vehicle page | Verify whether a Current Lease Customer is navigate to the email address verification page when the user clicks on "Skip" button | Y | CW_User_Story_836_05 | 6 | Medium | 4
1 | CMF - 836 | Verify whether the user is able to view the below links in the leasing a Toyota Vehicle page a. Apply for Credit b. College Grad Program c. Military Rebate d. Limited Credit Financing e. Special Offers f. Business Solutions | Verify the input address field | Y | CW_User_Story_836_06 | 5 | Medium | 4
1 | CMF - 836 | Verify whether the user is able to view and click the "FAQ" button in the leasing a Toyota Vehicle page | Verify the "City" input field | Functionality Not Yet Developed | CW_User_Story_836_07 | 7 | Medium | 4 |  |  |  |  | N/A- See All FAQs button and functionality is not delivered as part of sprint 1
1 | CMF - 836 | Verify whether the user is able to view the Disclaimer and Payment Estimator in the leasing a Toyota Vehicle page | Verify the "Zip code" input field | Y | CW_User_Story_836_08 | 6 | Medium | 4
1 | CMF - 839 | Verify whether the user is able to view the below options under Your Credit Score page 1. Global Header - Footer 2. Bread Crumb | As a current lease customer, I want to understand the options available to me at the end of my lease for purchasing my leased vehicle so I can make an informed decision | Not Automatable | CW_User_Story_839_01 | 4 | Medium | 4
1 | CMF - 839 | Verify whether the user is able to view the sub-menus under "Understanding Credit" and "Financing Options" heading under Your Credit Score page | Verify when the user clicks "purchase it" in the lease end options page | Not Automatable | CW_User_Story_839_02 | 3 | Medium | 4
1 | CMF - 839 | Verify whether the user is able to View the button / link for Credit Application under Your Credit Score page | Verify when the user clicks "I'm not sure" in the lease end options page | Not Automatable | CW_User_Story_839_03 | 4 | Medium | 4
1 | CMF - 839 | Verify whether the user is able to View the below links under Your Credit Score page <Little Credit experience> <its important to be proactive> | Verify the "Lease end overview page" | Y | CW_User_Story_839_04 | 4 | Medium | 4
1 | CMF - 862 | Verify whether the user is able to view the below options in the Business solutions page 1. Global Header - Footer 2. Bread Crumb | Verify when the user clicks "Purchase Vehicle" in the lease end overview page | Yet To Automate | CW_User_Story_862_01 | 4 | Medium | 4
1 | CMF - 862 | Verify whether the user is able to view the sub-menus under "For Business" and "Financing Options" heading options in the Business solutions page | As a current lease customer, I want to view the estimated purchase price my leased vehicle so I can decide whether or not I want to purchase it | Yet To Automate | CW_User_Story_862_02 | 3 | Medium | 4
1 | CMF - 862 | Verify whether the user is able to view the link for Customer Contact# in the Business solutions page | Verify when the user clicks "purchase it" in the lease end options page | Yet To Automate | CW_User_Story_862_03 | 3 | Medium | 4
1 | CMF - 862 | Verify whether the user is able to view the below links in the Business solutions page a. Vehicle Service Agreements b. Guaranteed Auto Protection c. Prepaid Maintenance d. Excess Wear & use | Verify when the user clicks "I'm not sure" in the lease end options page | Not Automatable | CW_User_Story_862_04 | 4 | Medium | 4
1 | CMF - 862 | Verify whether the user is able to view the 'FAQ' link in the Business solutions page | Verify the financing page | Not Automatable | CW_User_Story_862_05 | 6 | Medium | 4
1 | CMF - 862 | Verify whether the user is able to view the Disclaimer in the Business solutions page | Verify when the user clicks 'Yes' in Financing page | Yet To Automate | CW_User_Story_862_06 | 3 | Medium | 4
1 | CMF - 862 | Verify whether the user is able to view the link for Customer Contact# in the Business solutions page and click on Contact link# in the Mobile View | Verify when the user clicks 'I'm not sure' in Financing page | Yet To Automate | CW_User_Story_862_07 | 4 | Medium | 4
1 | CMF - 867 | Verify whether the user is able to view the general information about the company | Verify the "Lease Vehicle Purchase Estimator" page in default state. | Y | CW_User_Story_867_01 | 3 | Medium | 4
1 | CMF - 872 | Verify whether the user is able to view the below community related activities in the About US page i) Company Overview ii) Careers iii) Community iv) Fair Lending | Verify whether a Current Lease Customer is able to view the estimated purchase price | Y | CW_User_Story_872_01 | 4 | Medium | 4 |  |  |  |  | N/A- popup for External site is not developed
1 | CMF - 872 | Verify whether the user is able to view the below community related activities in the About US page and click on each of the external website link displayed in the page and also check the 'Return' button functionality is working i) Company Overview ii) Careers iii) Community iv) Fair Lending | Verify whether a Current Lease Customer is navigate to the email address verification page when the user clicks on "Skip" button | Functionality Not Yet Developed | CW_User_Story_872_02 | 5 | Medium | 4 |  |  |  |  | N/A- popup for External site is not developed
1 | CMF - 872 | Verify whether the user is able to view the below community related activities in the About US page and click on each of the external website link displayed in the page and also check the 'Continue' button functionality is working i) Company Overview ii) Careers iii) Community iv) Fair Lending | JS Component: Payment Estimator (Design update) | Functionality Not Yet Developed | CW_User_Story_872_03 | 5 | Medium | 4 |  |  |  |  | N/A- popup for External site is not developed
1 | CMF - 821 | Verify whether the user is able to visit additional websites associated with TFS from the Footer Accept Navigation | As an End of Term Lease Customer (< 61 days), I want the system to prompt me so that I can schedule an inspection for my leased vehicle (FED Integration) | Functionality Not Yet Developed | CW_User_Story_821_01 | 12 | Complex | 8 |  |  |  |  | N/A- popup for External site is not developed
1 | CMF - 821 | Verify whether the user is able to visit additional websites associated with TFS from the Footer Decline Navigation | As a Customer, I want to request that a dealer contact me so that I can purchase my leased vehicle, purchase a new vehicle, or lease a new vehicle (Functional) | Functionality Not Yet Developed | CW_User_Story_821_02 | 12 | Complex | 8 |  |  |  |  | N/A- popup for External site is not developed
1 | CMF - 822 | Verify that the user is able to find social media options in the Footer to follow Toyota | As a Customer, I want to search for dealer contact information so I can contact a specific dealer (Search/Functional) | Functionality Not Yet Developed | CW_User_Story_822_01 | 7 | Medium | 4 |  |  |  |  | Defect is in Deferred Status
1 | CMF - 823 | Verify that the user is able to connect to the Toyota USA Page in Instagram - Global Footer | CMS Component: Breadcrumbs | Functionality Not Yet Developed | CW_User_Story_823_01 | 3 | Medium | 4 |  |  |  |  | Defect is in Deferred Status
1 | CMF - 825 | Verify that the user is able to provide feedback about privacy practices - Global Footer | CMS Component: Footer | Functionality Not Yet Developed | CW_User_Story_825_01 | 3 | Medium | 4 |  |  |  |  | Links for Privacy Feedback has not been delivered
1 | CMF - 826 | Verify that the TFS Web site owner displays copyright details - Global Footer | CMS Component: Nav | Y | CW_User_Story_826_01 | 3 | Medium | 4
1 | CMF - 827 | Verify the TFS affiliation with Toyota Motors and Privacy policy - Global Footer | JS Component: Lease End Overview | Y | CW_User_Story_827_01 | 2 | Medium | 4
1 | CMF - 832 | Verify the Site Map option in the Footer | Verify the "Lease end overview page" | Y | CW_User_Story_832_01 | 5 | Medium | 4
1 | CMF - 832 | Verify the recent update provided to the Site Map | Verify when the user clicks "Get a new lease" in the lease end overview page | Functionality Not Yet Developed | CW_User_Story_832_02 | 13 | Complex | 8
1 | CMF - 835 | Verify the Buy a Toyota Sub-Menu | Verify when the user clicks "Return vehicle" in the lease end overview page | Functionality Not Yet Developed | CW_User_Story_835_01 | 6 | Medium | 4 |  |  |  |  | Content Copy has been verified -Partially Executed(Defects has been raised)(Links under Financing options are not fully developed)
1 | CMF - 835 | Verify whether the user is able to navigate to the respective pages on clicking links available under Buy a Toyota option | Verify when the user clicks "Purchase vehicle" in the lease end overview page | Functionality Not Yet Developed | CW_User_Story_835_02 | 13 | Complex | 8 |  |  |  |  | N/A- All the links under Financing options are not fully developed
1 | CMF - 838 | Verify the 'What Credit Is' Menu Move to External website | Verify when the user enters a search keyword in the lease end overview page | Functionality Not Yet Developed | CW_User_Story_838_01 | 11 | Complex | 8 |  |  |  |  | N/A for Step 9, 10 & 11
1 | CMF - 838 | Verify the 'What Credit Is' Menu Stay on the Current Page | JS Component: Input Label Updates | Functionality Not Yet Developed | CW_User_Story_838_02 | 11 | Complex | 8 |  |  |  |  | N/A for Step 9, 10 & 11
1 | CMF - 861 | Verify the 'For Business' sub-menu in global header under Financing option menu | JS Component: Layout Updates | Y | CW_User_Story_861_01 | 6 | Medium | 4
1 | CMF - 871 | Verify the 'Careers' option under 'About Us' Leave Current Page | JS Component: Contact Dealer | Functionality Not Yet Developed | CW_User_Story_871_01 | 5 | Medium | 4 |  |  |  |  | N/A- Popup for external site is not yet developed
1 | CMF - 871 | Verify the 'Careers' option under 'About Us' Stay on Current Page | JS Component: Request Dealer contact (FED Integration) | Functionality Not Yet Developed | CW_User_Story_871_02 | 5 | Medium | 4 |  |  |  |  | N/A- Popup for external site is not yet developed
1 | CMF - 830 | Verify whether the user is able to access the FAQ's Page from the Global Navigation Header | As a Prospect or Customer, I want to understand the end of lease process and the options available to me at the end of a lease | Functionality Not Yet Developed | CW_User_Story_830_01 | 13 | Complex | [5 empty] | N/A- Navigation links and FAQ's links are not accessible in header
1 | CMF - 830 | Verify the content of FAQ's page | Verify the "Lease End options" page | Yet To Automate | CW_User_Story_830_02 | 7 | Medium
1 | CMF - 830 | Verify the "About Us" category in FAQ's page | Verify when the user clicks "return it" in the lease end options page | Yet To Automate | CW_User_Story_830_03 | 5 | Medium
1 | CMF - 830 | Verify the "I'm shopping for a new car" category in FAQ's page | Verify when the user clicks "replace it" in the lease end options page | Yet To Automate | CW_User_Story_830_04 | 9 | Medium
1 | CMF - 830 | Verify the "I need to set up my account" category in FAQ's page | Verify when the user clicks "I'm not sure" in the lease end options page | Yet To Automate | CW_User_Story_830_05 | 9 | Medium
1 | CMF - 830 | Verify the "I need to manage my account" category in FAQ's page | Verify the "Lease end overview page" | Functionality Not Yet Developed | CW_User_Story_830_06 | 14 | Complex | [5 empty] | Pending Clarification
1 | CMF - 830 | Verify the "Lease End:" category in FAQ's page | Verify when the user clicks "Get a new lease" in the lease end overview page | Yet To Automate | CW_User_Story_830_07 | 7 | Medium
1 | CMF - 830 | Verify whether the user is able to see the list of questions as suggestions when the user types the questions | Verify when the user clicks "Return vehicle" in the lease end overview page | Functionality Not Yet Developed | CW_User_Story_830_08 | 6 | Medium | [5 empty] | N/A- This will be part of Adobe Search which will be developed in upcoming sprints
1 | CMF - 830 | Verify whether the systems provides the auto-correct when the user types incorrect spelling | Verify when the user clicks "Purchase Vehicle" in the lease end overview page | Functionality Not Yet Developed | CW_User_Story_830_09 | 3 | Medium | [5 empty] | N/A- This will be part of Adobe Search which will be developed in upcoming sprints
1 | CMF - 830 | Verify whether the User is able to see the Answers for the Questions selected |  | Yet To Automate | CW_User_Story_830_10 | 3 | Medium
1 | CMF - 824 | Verify whether the user is able to install TFS app on their iPhone |  | Functionality Not Yet Developed | CW_User_Story_824_01 | 3 | Medium | [5 empty] | N / A - Links does not navigate to App Store and not delivered
1 | CMF - 824 | Verify whether the user is able to install TFS app on their android |  | Functionality Not Yet Developed | CW_User_Story_824_01 | 3 | Medium | [5 empty] | N / A - Links does not navigate to Play Store and not delivered

## Estimations
Sprints | Manual Test Case Total | Automatable | Simple | Medium | Complex | Estimated Hours Per Resource | Estimated Days Per Resource | Resources | Planned Days for Given Resources | Actual Hours Taken | Actual Days Taken | Comments
Sprint-1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
Sprint-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
Sprint-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
Sprint-4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
Sprint-5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
Sprint-6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
Sprint-7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
Sprint-8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
Sprint-9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
Sprint-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
Sprint-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0

## Script-Develepment
Sprints | Manual test case Total | Planned Target(%) | Actual Target(%) | Test cases Automated | Defect Found in Automation | Comments
Sprint-1 | 0 | 50 | 0 | 0
Sprint-2 | 0 | 50 | 0 | 0 | .
Sprint-3 | 0 | 50 | 0 | 0
Sprint-4 | 0 | 50 | 0 | 0
Sprint-5 | 0 | 50 | 0 | 0
Sprint-6 | 0 | 50 | 0 | 0 | 3
Sprint-7 | 0 | 50 | 0 | 0
Sprint-8 | 0 | 50 | 0 | 0
Sprint-9 | 0 | 50 | 0 | 0
Sprint-10 | 0 | 50 | 0 | 0
Sprint-11 | 0 | 50 | 0 | 0
TOTAL | 0 | 50 | 0 | 0 | 3

## Execution-Regression
Sprint | Date Of Execution | Executed Environment | Total Automated | Executed | Passed TC's | Failed TC's | Total duration | Failure Reasons | Defects Found | Defects ID's
|  | Chrome | 0
|  | IOS | 0
|  | Android | 0
|  | Chrome | 0
|  | IOS | 0
|  | Android | 0
|  | Chrome | 0
|  | IOS | 0
|  | Android | 0
|  | Chrome | 0
|  | IOS | 0
|  | Android | 0
|  | Chrome | 0
|  | IOS | 0
|  | Android | 0
|  | Chrome | 0
|  | IOS | 0
|  | Android | 0
|  | Chrome | 0
|  | IOS | 0
|  | Android | 0

## Execution-Compatibility-Sprint1
|  | Date | Executed | Passed TC's | Failed TC's | Total Duration In Hours | Failure Reasons | Defects Found | Defects ID's
Desktop Browsers | Chrome
IE
Firefox
Mobile Devices | iPad (latest)
Galaxy Tab (latest)
Samsung Edge
iPhone 7
iPhone 7 Plus
iPhone 6
iPhone 5S
Galaxy S7
Galaxy S6
Galaxy S5
Galaxy Note 5
Galaxy Note 4
Motorola
HTC One