## Sheet2 (hidden)
Module | Use cases | Device Name
Registration | 01-Registration | Desktop (Website)
| 42-Registration | Mobile Web
| 14-Registration Scanning QA Code & Manual Entry | Mobile App
Authentication | pending | Desktop (Website)
| 1-Authentication (Conversion included) | Mobile Web
| 13-Authentication Website Registered Users | Mobile App
12-Authentication (Login for Mobile App Registered Users)
Forgot Username | 03-Forgot Username | Desktop (Website)
| 03-Forgot Username | Mobile Web
| 15-Retrieving a Forgotten Username - pending | Mobile App
Forgot Password | 04- Forgot Password Website | Desktop (Website)
| 04-Forgot Password | Mobile Web
| 16-Reset a Forgotten Password - pending | Mobile App
Session Time Out | 23-session timeout_website | Desktop (Website)
| 23-session timeout_Mob Web | Mobile Web
| 23-session timeout_Mob app | Mobile App
Unlockin an Account | 17-Unlocking an Account-pending | Mobile App

## Sheet3 (hidden)
Mobile Web | Alternate Flows (exception cases) | Yet to Receive | 23
Mobile Web | Conversion |  | 25
Mobile Web | Profile |  | 34
Legacy Desktop | Conversion Redirection |  | 25
Legacy Desktop | Alternate Flows (exception cases) Redirection |  | 10
Legacy Desktop | Profile Redirection |  | 25
mApp Android | Profile & Conversion |  | 34
mApp iOS | Profile & Conversion |  | 20
mApp Android | Self-service (Forgot UN, Forgot Pswd) Alternate Flows (exception cases) |  | 20
eMails | Email Templates & Service |  | 20

## Test Case Estimate-New
Mobile First-Option2 |  |  | TC count | [10 empty] | Preparation Effort |  | Execution Effort
Deliverable# as per SOW | Channel Name | Module /Function as per SOW | TFS | LFS | iOS |  | Android |  | No of Test cases | Test Case to be prepared | Test Case to be executed | Retest Count (20%) | Total Test Case to be executed | Prepration Effort (in Minutes) | Preparation Effort (in Hours) | Execution Effort (in Minutes) | Execution Effort (in Hours)
[5 empty] | TFS | LFS | TFS | LFS
D2 | Website | Login | 35 | 35 | 0 | 0 | 0 | 0 | 70 | 70 | 70 | 14 | 84 | 2800 | 46.6667 | 4200 | 70
|  | RBA | 12 | 12 | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 4.8 | 28.8 | 960 | 16 | 1440 | 24
|  | MFA Login | 36 | 36 | 0 | 0 | 0 | 0 | 72 | 72 | 72 | 14.4 | 86.4 | 2880 | 48 | 4320 | 72
|  | MFA Converion | 40 | 40 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 16 | 96 | 3200 | 53.3333 | 4800 | 80
D3 | Website | EBA/OC Reacceptance | 18 | 18 | 0 | 0 | 0 | 0 | 36 | 36 | 36 | 7.2 | 43.2 | 1440 | 24 | 2160 | 36
|  | Registration | 35 | 35 | 0 | 0 | 0 | 0 | 70 | 70 | 70 | 14 | 84 | 2800 | 46.6667 | 4200 | 70
|  | Token Registration | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 4 | 24 | 800 | 13.3333 | 1200 | 20
D4 | Website | Forgot Username | 16 | 16 | 0 | 0 | 0 | 0 | 32 | 32 | 32 | 6.4 | 38.4 | 1280 | 21.3333 | 1920 | 32
|  | Forgot Password | 15 | 15 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 6 | 36 | 1200 | 20 | 1800 | 30
|  | Forgot SQA | 12 | 12 | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 4.8 | 28.8 | 960 | 16 | 1440 | 24
|  | Mini Registration | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 4 | 24 | 800 | 13.3333 | 1200 | 20
D5 | Website | Account Overview | 45 | 45 | 0 | 0 | 0 | 0 | 90 | 90 | 90 | 18 | 108 | 3600 | 60 | 5400 | 90
|  | Add Accounts | 22 | 22 | 0 | 0 | 0 | 0 | 44 | 44 | 44 | 8.8 | 52.8 | 1760 | 29.3333 | 2640 | 44
|  | Add Multiple Accounts | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 4 | 24 | 800 | 13.3333 | 1200 | 20
|  | Remove Account | 12 | 12 | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 4.8 | 28.8 | 960 | 16 | 1440 | 24
|  | View Contract Info | 8 | 8 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 3.2 | 19.2 | 640 | 10.6667 | 960 | 16
D6 | Website | Account History | 20 | 20 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 8 | 48 | 1600 | 26.6667 | 2400 | 40
|  | View Agreements | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 4 | 24 | 800 | 13.3333 | 1200 | 20
|  | Go Paperless - Billing Statement | 15 | 15 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 6 | 36 | 1200 | 20 | 1800 | 30
|  | Multiple Go Paperless | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 4 | 24 | 800 | 13.3333 | 1200 | 20
|  | Go Paperless - ePrivacy, IVR/ER | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 4 | 24 | 800 | 13.3333 | 1200 | 20
D7 | Website | My Profile - Change Username, Password, SQA | 12 | 12 | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 4.8 | 28.8 | 960 | 16 | 1440 | 24
|  | My Profile - Change Account Management Email, Information Email | 13 | 13 | 0 | 0 | 0 | 0 | 26 | 26 | 26 | 5.2 | 31.2 | 1040 | 17.3333 | 1560 | 26
|  | Address Change | 6 | 6 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 2.4 | 14.4 | 480 | 8 | 720 | 12
|  | Change Privacy Options | 6 | 6 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 2.4 | 14.4 | 480 | 8 | 720 | 12
|  | Change Marketing Preference | 4 | 4 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 1.6 | 9.6 | 320 | 5.3333 | 480 | 8
|  | MFA Preferences | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 4 | 24 | 800 | 13.3333 | 1200 | 20
D8 | Website | View Statement | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 4 | 24 | 800 | 13.3333 | 1200 | 20
|  | View Privacy Notice | 8 | 8 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 3.2 | 19.2 | 640 | 10.6667 | 960 | 16
|  | View IVR/ER Notice | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 4 | 24 | 800 | 13.3333 | 1200 | 20
|  | View Legal Servicing Notice | 5 | 5 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 2 | 12 | 400 | 6.6667 | 600 | 10
|  | Change Account Notification | 6 | 6 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 2.4 | 14.4 | 480 | 8 | 720 | 12
|  | Change Pay online Notification | 8 | 8 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 3.2 | 19.2 | 640 | 10.6667 | 960 | 16
|  | Throttling for EBA/OC | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 4 | 24 | 800 | 13.3333 | 1200 | 20
D9 | Website | Citi/Kubra & Salesforce Integration | 50 | 50 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 20 | 120 | 4000 | 66.6667 | 6000 | 100
|  | Header & Footer for Citi | 25 | 25 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 10 | 60 | 2000 | 33.3333 | 3000 | 50
|  | Support Center/Case Mgmt/DDC | 20 | 20 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 8 | 48 | 1600 | 26.6667 | 2400 | 40
|  | Contact Us(Non Secure Email) | 5 | 5 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 2 | 12 | 400 | 6.6667 | 600 | 10
D2 | Mobile Web | Login | 35 | 35 | 0 | 0 | 0 | 0 | 70 | 0 | 70 | 14 | 84 | 0 | 0 | 4200 | 70
|  | RBA | 12 | 12 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 4.8 | 28.8 | 0 | 0 | 1440 | 24
|  | MFA Login | 36 | 36 | 0 | 0 | 0 | 0 | 72 | 0 | 72 | 14.4 | 86.4 | 0 | 0 | 4320 | 72
|  | MFA Converion | 40 | 40 | 0 | 0 | 0 | 0 | 80 | 0 | 80 | 16 | 96 | 0 | 0 | 4800 | 80
D3 | Mobile Web | EBA/OC Reacceptance | 18 | 18 | 0 | 0 | 0 | 0 | 36 | 0 | 36 | 7.2 | 43.2 | 0 | 0 | 2160 | 36
|  | Registration | 35 | 35 | 0 | 0 | 0 | 0 | 70 | 0 | 70 | 14 | 84 | 0 | 0 | 4200 | 70
|  | Token Registration | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 4 | 24 | 0 | 0 | 1200 | 20
D4 | Mobile Web | Forgot Username | 16 | 16 | 0 | 0 | 0 | 0 | 32 | 0 | 32 | 6.4 | 38.4 | 0 | 0 | 1920 | 32
|  | Forgot Password | 15 | 15 | 0 | 0 | 0 | 0 | 30 | 0 | 30 | 6 | 36 | 0 | 0 | 1800 | 30
|  | Forgot SQA | 12 | 12 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 4.8 | 28.8 | 0 | 0 | 1440 | 24
|  | Mini Registration | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 4 | 24 | 0 | 0 | 1200 | 20
D5 | Mobile Web | Account Overview | 45 | 45 | 0 | 0 | 0 | 0 | 90 | 0 | 90 | 18 | 108 | 0 | 0 | 5400 | 90
|  | Add Accounts | 22 | 22 | 0 | 0 | 0 | 0 | 44 | 0 | 44 | 8.8 | 52.8 | 0 | 0 | 2640 | 44
|  | Add Multiple Accounts | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 4 | 24 | 0 | 0 | 1200 | 20
|  | Remove Account | 12 | 12 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 4.8 | 28.8 | 0 | 0 | 1440 | 24
|  | View Contract Info | 8 | 8 | 0 | 0 | 0 | 0 | 16 | 0 | 16 | 3.2 | 19.2 | 0 | 0 | 960 | 16
D6 | Mobile Web | Account History | 20 | 20 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 8 | 48 | 0 | 0 | 2400 | 40
|  | View Agreements | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 4 | 24 | 0 | 0 | 1200 | 20
|  | Go Paperless - Billing Statement | 15 | 15 | 0 | 0 | 0 | 0 | 30 | 0 | 30 | 6 | 36 | 0 | 0 | 1800 | 30
|  | Multiple Go Paperless | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 4 | 24 | 0 | 0 | 1200 | 20
|  | Go Paperless - ePrivacy, IVR/ER | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 4 | 24 | 0 | 0 | 1200 | 20
D7 | Mobile Web | My Profile - Change Username, Password, SQA | 12 | 12 | 0 | 0 | 0 | 0 | 24 | 0 | 24 | 4.8 | 28.8 | 0 | 0 | 1440 | 24
|  | My Profile - Change Account Management Email, Information Email | 13 | 13 | 0 | 0 | 0 | 0 | 26 | 0 | 26 | 5.2 | 31.2 | 0 | 0 | 1560 | 26
|  | Address Change | 6 | 6 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 2.4 | 14.4 | 0 | 0 | 720 | 12
|  | Change Privacy Options | 6 | 6 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 2.4 | 14.4 | 0 | 0 | 720 | 12
|  | Change Marketing Preference | 4 | 4 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 1.6 | 9.6 | 0 | 0 | 480 | 8
|  | MFA Preferences | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 4 | 24 | 0 | 0 | 1200 | 20
D8 | Mobile Web | View Statement | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 4 | 24 | 0 | 0 | 1200 | 20
|  | View Privacy Notice | 8 | 8 | 0 | 0 | 0 | 0 | 16 | 0 | 16 | 3.2 | 19.2 | 0 | 0 | 960 | 16
|  | View IVR/ER Notice | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 4 | 24 | 0 | 0 | 1200 | 20
|  | View Legal Servicing Notice | 5 | 5 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 2 | 12 | 0 | 0 | 600 | 10
|  | Change Account Notification | 6 | 6 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 2.4 | 14.4 | 0 | 0 | 720 | 12
|  | Change Pay online Notification | 8 | 8 | 0 | 0 | 0 | 0 | 16 | 0 | 16 | 3.2 | 19.2 | 0 | 0 | 960 | 16
|  | Throttling for EBA/OC | 10 | 10 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 4 | 24 | 0 | 0 | 1200 | 20
D9 | Mobile Web | Citi/Kubra & Salesforce Integration | 50 | 50 | 0 | 0 | 0 | 0 | 100 | 0 | 100 | 20 | 120 | 0 | 0 | 6000 | 100
|  | Header & Footer for Citi | 25 | 25 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 10 | 60 | 0 | 0 | 3000 | 50
|  | Support Center/Case Mgmt/DDC | 20 | 20 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 8 | 48 | 0 | 0 | 2400 | 40
|  | Contact Us(Non Secure Email) | 5 | 5 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 2 | 12 | 0 | 0 | 600 | 10
Total |  |  | 1218 | 1218 | 0 | 0 | 0 | 0 | 2436 | 1218 | 2436 | 487.2 | 2923.2 | 48720 | 812 | 146160 | 2436

## Revised Effort
# | Test Design Effort | Effort in Hours | Effort In person Days
1 | Test Case Preparation Effort | 812 | 101.5
2 | AEM Test Case Preparation (20% of Functional effort) | 162.4 | 20.3
3 | Copy Deck & Email Templates Test Case Preparation
a | Functional Test Case (75 Test Cases) | 50 | 6.25
b | Copy Deck Content (75 Test Cases) | 50 | 6.25
c | EBA/OC - Throtlling(75 Test Cases) | 50 | 6.25
7 | E2E Test Case Preparation(30% of Functional effort) | 162.4 | 20.3
Total Test Design Effort |  | 1286.8 | 160.85
# | Test Execution Effort | Effort in Hours | Effort In person Days
TEST Environment
1 | Functional Test Execution Effort | 2436 | 304.5
2 | AEM Test Execution (20% of Functional effort) | 487.2 | 60.9
3 | Copy Deck & Email Templates(225 Test Cases) Test Execution | 187.5 | 23.4375
4 | Regression Testing For Every Sprint(25% of Functional Testing) | 777.675 | 97.2094
5 | Compatibility Testing (30% of functional Test cases, executed in various devices and browsers) | 933.21 | 116.6512
| Total Test Execution Effort in TEST | 4821.585 | 602.6981
STAGE Environment
1 | Test Execution Effort - STAGE (40%) | 1244.28 | 155.535
2 | E2E Test Execution in STAGE (30%) | 730.8 | 91.35
| Total Test Execution Effort In STAGE | 1975.08 | 246.885
Overall Test Execution Effort |  | 6796.665 | 849.5831
Automation Effort(TEST& STAGE)
1 | Test Automation Effort(including automated Regression Test execution) | 5846.4 | 730.8
Automation Effort(TEST& STAGE)
1 | Performance Testing Effort(including components and UI) | 2890 | 361.25
Test Management Effort(TEST& STAGE)
1 | Test Management Effort(20%) | 1616.693 | 202.0866
Total Overall Effort |  | 18436.558 | 2304.5697

## ConsultantSheet
|  |  | June |  | July |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
Roles | Grade | Location | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20 | 2018-08-27 | 2018-09-03 | 2018-09-10 | 2018-09-17 | 2018-09-24 | 2018-10-01 | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | Total PDs | Hours /Day | Rate/Hr | Total Effort In Hours | Total Cost
|  | Days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Test Manager | G8/G9 | Onsite | [29 empty] | 0 | 8 | 75 | 0 | 0
|  | Offshore | [29 empty] | 0 | 8.75 | 25 | 0 | 0
|  | Nearshore | [29 empty] | 0 | 9 |  | 0 | 0
Test Lead | G6/G7 | Onsite | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 72.5 | 8 | 70 | 580 | 40600
|  | Offshore | [29 empty] | 0 | 8.75 | 25 | 0 | 0
|  | Nearshore | [29 empty] | 0 | 9 |  | 0 | 0
Test Automation Architect |  | Onsite | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 72.5 | 8 | 70 | 580 | 40600
| G5/6 | Offshore | [29 empty] | 0 | 8.75 | 22 | 0 | 0
|  | Nearshore | [29 empty] | 0 | 9 | 45 | 0 | 0
Performance Test Architect | G5/6 | Onsite | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 72.5 | 8 | 70 | 580 | 40600
|  | Offshore | [29 empty] | 0 | 8.75 |  | 0 | 0
|  | Nearshore | [29 empty] | 0 | 9 | 45 | 0 | 0
U/X Consultant |  | Onsite | [29 empty] | 0 | 8 | 70 | 0 | 0
| G3/4 | Offshore | [29 empty] | 0 | 8.75 | 22 | 0 | 0
|  | Nearshore | [29 empty] | 0 | 9 |  | 0 | 0
Functional |  | Onsite | [29 empty] | 0 | 8 | 70 | 0 | 0
| G3/4 | Offshore | 3 | 3 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 5 | 5 | 880 | 8.75 | 22 | 7700 | 169400
|  | Nearshore | [29 empty] | 0 | 9 |  | 0 | 0
Automation Consultants |  | Onsite | [29 empty] | 0 | 8 |  | 0 | 0
| G3/4 | Offshore | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 580 | 8.75 | 22 | 5075 | 111650
|  | Nearshore | [29 empty] | 0 | 9 |  | 0 | 0
Performance Test Consultants |  | Onsite | [29 empty] | 0 | 8 | 70 | 0 | 0
|  | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 325 | 8.75 | 22 | 2843.75 | 62562.5
| G3/4 | Nearshore | [29 empty] | 0 | 8 | 31.26 | 0 | 0
Total |  |  | 5.5 | 5.5 | 9.5 | 9.5 | 9.5 | 9.5 | 10.5 | 11.5 | 11.5 | 12.5 | 13.5 | 15.5 | 16.5 | 16.5 | 16.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 17.5 | 11.5 | 11.5 | 11.5 | 2002.5 |  |  | 17358.75 | 465412.5