## COMPONENTS PLANNED
Column1 | STEPS | COMPLEXITY | DEVELOPER | STATUS | DESCRIPTION | AUTOMATION DEVELOPER | CODE REVIEW DATE | AUTOMATION LEAD/CoE | CODE REVIEW COMMENTS | Column1
CW_Login | 10 | Low (1-10) | Automation Team | New
CW_RBA | 12 | Medium (11-20) | Automation Team | New
CW_MFA_Login | 22 | High (21 to 50) | Automation Team | New
CW_MFA_Converion | 30 | High (21 to 50) | Automation Team | New
CW_EBA_OC_Reacceptance | 15 | Medium (11-20) | Automation Team | New
CW_Registration | 50 | High (21 to 50) | Automation Team | New
CW_Token_Registration | 15 | Medium (11-20) | Automation Team | New
CW_Forgot_Username | 15 | Medium (11-20) | Automation Team | New
CW_Forgot_Password | 15 | Medium (11-20) | Automation Team | New
CW_Forgot_SQA_ | 10 | Low (1-10) | Automation Team | New
CW_Mini_Registration | 12 | Medium (11-20) | Automation Team | New
CW_Account_Overview | 22 | High (21 to 50) | Automation Team | New
CW_Add__Accounts | 20 | Medium (11-20) | Automation Team | New
CW_Add_Multiple_Accounts | 20 | Medium (11-20) | Automation Team | New
CW_Remove_Account | 10 | Low (1-10) | Automation Team | New
CW_View_Contract_Info | 12 | Medium (11-20) | Automation Team | New
CW_Account_History | 22 | High (21 to 50) | Automation Team | New
CW_View_Agreements | 15 | Medium (11-20) | Automation Team | New
CW_Go_Paperless_Billing_Statement | 15 | Medium (11-20) | Automation Team | New
CW_Multiple_Go_Paperless | 18 | Medium (11-20) | Automation Team | New
CW_Go_Paperless_ePrivacy_IVR_ER | 17 | Medium (11-20) | Automation Team | New
CW_My_Profile_Change_Username_Password_SQA | 22 | High (21 to 50) | Automation Team | New
CW_My_Profile_Change_Account_Management_Email_Information_Email | 24 | High (21 to 50) | Automation Team | New
CW_Address_Change | 20 | Medium (11-20) | Automation Team | New
CW_Change_Privacy_Options | 24 | High (21 to 50) | Automation Team | New
CW_Change_Marketing_Preference | 22 | High (21 to 50) | Automation Team | New
CW_MFA_Preferences | 13 | Medium (11-20) | Automation Team | New
CW_View_Statement | 22 | High (21 to 50) | Automation Team | New
CW_View_Privacy_Notice | 10 | Low (1-10) | Automation Team | New
CW_View_IVR_ER_Notice | 10 | Low (1-10) | Automation Team | New
CW_View_Legal_Servicing_Notice | 10 | Low (1-10) | Automation Team | New
CW_Change_Account_Notification | 10 | Low (1-10) | Automation Team | New
CW_Change_Pay_online_Notification | 10 | Low (1-10) | Automation Team | New
CW_Throttling_for_EBA_OC | 22 | High (21 to 50) | Automation Team | New
CW_Citi_Kubra_alesforce_Integration | 18 | Medium (11-20) | Automation Team | New
CW_Header_Footer_for_Citi | 15 | Medium (11-20) | Automation Team | New
CW_Support_Center_Case_Mgmt_DDC | 10 | Low (1-10) | Automation Team | New
CW_Contact_Us(Non_Secure_Email) | 12 | Medium (11-20) | Automation Team | New
CW_Buffer1 | 15 | Medium (11-20) | Automation Team | New
CW_Buffer2 | 15 | Medium (11-20) | Automation Team | New
CW_Buffer3 | 15 | Medium (11-20) | Automation Team | New
CW_Buffer4 | 15 | Medium (11-20) | Automation Team | New
CW_Buffer5 | 15 | Medium (11-20) | Automation Team | New
CW_Buffer6 | 15 | Medium (11-20) | Automation Team | New
CW_Buffer7 | 15 | Medium (11-20) | Automation Team | New
CW_Buffer8 | 15 | Medium (11-20) | Automation Team | New
CW_Buffer9 | 15 | Medium (11-20) | Automation Team | New
CW_Buffer10 | 15 | Medium (11-20) | Automation Team | New
Last Row
Note on A1: Jim Sears: Add additional components: Right click a row number on the left like the number 2. From the context menu for right-click, select Insert. Add multiple rows by selecting multiple row numbers like 2 through 10 by using the shift key.

## ESTIMATION INTRODUCTION
Introduction
Automation LOE (level of effort) relies on several key factors to generate an accurate estimation but even then, the estimation accuracy is +/- 30%.
Key factors to the effort are skill level and automation tool compatibility. If the tools can't work with the application then automation is not at all possible.Skill level will impact the productivity level as developers resolve unexpected issues during scripting.
The TAF framework has several features to automatically complete tasks. The manual tasks consume significant amount time so if the TAF BPT version is used then please be aware that productivity and accuracy are impacted.
TAF ACTION and TAF STEP eliminates much of the Test Planning effort as Test Steps are automatically captured and updated during test execution and are kept in sync during future execution too where maintenance in BPT is ongoing effort that must be accounted for.
Non-linear systems that need flexibility over reuse can use TAF Step Based. TAF Step also updates Test Steps automatically saving time and improving accuracy in the documentation.
Usage
The automation effort is divided into multiple parts so that each part can be calucated for a single set of circumstances. Part A cirucmstances could be for "medium complexity" components with automation developers of "Beginner" experience.
Part B could be for "high complexity" components with "Difficult or dynamic" object recognition. Providing estimation that accounts for different circumstances will improve the overall accuracy of the LOE estimation.
NOTE: The estimation is based on a double weighted system that is managed and defined by CoE. The inputs are guided by the yellow shaded cells and will produce the total LOE, in hours.
NOTE: The project length and resources are not part of the LOE estimation but can be include at the end to gauge the project length.

## ESTIMATION
StepsCnt | Entity and Values | Mulitpliers | Weight: Sum%100
| AUT |  | 2% | Part A Entity |  | Value | Multiplier | Weight | SubTotal | Estimate | Weeks |  | # Components | Framework | Complexity | LOE
| COTS (Commercial) | 1 |  | Manager Supervision | -> | 25% | -- | -- | 43.4 | 217 | 5.43 | Part A | 10 | TAF ACTION | Low (1-10) | 217
| Developed in-house | 5 |  | # Component Count (Screens) | -> | 10 | 40 | -- | 40 |  |  | Part B | 27 | TAF ACTION | Medium (11-20) | 896
| Architecture |  | 0% | Test Case Complexity | -> | Low (1-10) | 4 | -- | -- |  |  | Part C | 11 | TAF ACTION | High (21 to 50) | 608
| Supported | 1 |  | AUT | -> | COTS (Commercial) | 1 | 2% | 0.8 |  |  | Part D | 0 | TAF ACTION | Complex (>51) | 0
| Not-supported | Unsupported |  | Architecture | -> | Supported | 1 | 0% | 0
| Tool Object Recognition |  | 10% | Tool Object Recognition | -> | Dynamic or difficult | 15 | 10% | 60
| Easily recognized | 1 |  | Working Prototype | -> | POC completed | 1 | 5% | 2
| Average | 7 |  | Application Flow | -> | Non-Linear | 3 | 5% | 6
| Dynamic or difficult | 15 |  | Framework | -> | TAF ACTION | 6 | 35% | 84
| Not recognized | Unsupported |  | Data Intensive | -> | Heavy data input | 4 | 3% | 4.8
| Working Prototype |  | 5% | Viable Test Data Source | -> | Data available | 1 | 5% | 2
| POC completed | 1 |  | Skill Level | -> | Expert | 1 | 35% | 14
| POC not-completed | 5 |  |  |  |  | Sub Total | 100% | 217
| Application Flow |  | 5%
| Linear | 1 |  | Part B Entity |  | Value | Multiplier | Weight | SubTotal | Estimate | Weeks
| Component/Process | 2 |  | Manager Supervision | -> | 25% | -- | -- | 179.01 | 896 | 22.4
| Non-Linear | 3 |  | # Component Count (Screens) | -> | 27 | 162 | -- | 162
| Framework |  | 35% | Test Case Complexity | -> | Medium (11-20) | 6 | -- | --
| TAF BPT | 10 |  | AUT | -> | Developed in-house | 5 | 2% | 16.2
| TAF ACTION | 6 |  | Architecture | -> | Supported | 1 | 0% | 0
| Custom | 4 |  | Tool Object Recognition | -> | Dynamic or difficult | 15 | 10% | 243
| TAF STEP | 2 |  | Working Prototype | -> | POC completed | 1 | 5% | 8.1
| Data Intensive |  | 3% | Application Flow | -> | Non-Linear | 3 | 5% | 24.3
| Light data input | 2 |  | Framework | -> | TAF ACTION | 6 | 35% | 340.2
| Heavy data input | 4 |  | Data Intensive | -> | Heavy data input | 4 | 3% | 19.44
| Test Case Complexity |  | -- | Viable Test Data Source | -> | Data available | 1 | 5% | 8.1
11 | Low (1-10) | 4 |  | Skill Level | -> | Expert | 1 | 35% | 56.7
21 | Medium (11-20) | 6 |  |  |  |  | Sub Total | 100% | 895.05
51 | High (21 to 50) | 10
200 | Complex (>51) | 14 |  | Part C Entity |  | Value | Multiplier | Weight | SubTotal | Estimate | Weeks |  | COMPLEXITY | COMPONENTS PLANNED | ESTIMATION
| Viable Test Data Source |  | 5% | Manager Supervision | -> | 25% | -- | -- | 121.55 | 608 | 15.2 |  | Low (1-10) | 9 | 10
| Data available | 1 |  | # Component Count (Screens) | -> | 11 | 110 | -- | 110 |  |  |  | Medium (11-20) | 28 | 27
| Data not-available | 5 |  | Test Case Complexity | -> | High (21 to 50) | 10 | -- | -- |  |  |  | High (21 to 50) | 11 | 11
| Skill Level |  | 35% | AUT | -> | Developed in-house | 5 | 2% | 11 |  |  |  | Complex (>51) | 0 | 0
| Beginner | 12 |  | Architecture | -> | Supported | 1 | 0% | 0 |  |  |  |  | Total Components | 48
| Experienced | 6 |  | Tool Object Recognition | -> | Dynamic or difficult | 15 | 10% | 165 |  |  |  |  | Estimation LOE | 1730
| Expert | 1 |  | Working Prototype | -> | POC completed | 1 | 5% | 5.5
|  |  |  | Application Flow | -> | Non-Linear | 3 | 5% | 16.5
|  |  |  | Framework | -> | TAF ACTION | 6 | 35% | 231 |  |  |  |  | Project Details
|  |  |  | Data Intensive | -> | Heavy data input | 4 | 3% | 13.2 |  |  |  |  | Resource Count | 1
|  |  |  | Viable Test Data Source | -> | Data available | 1 | 5% | 5.5 |  |  |  |  | Hours per Component | 37
|  |  |  | Skill Level | -> | Expert | 1 | 35% | 38.5 |  |  |  |  | Length (Weeks) | 44
[7 empty] | Sub Total | 100% | 607.75
|  |  |  | Part D Entity |  | Value | Multiplier | Weight | SubTotal | Estimate | Weeks
|  |  |  | Manager Supervision | -> | 15% | -- | -- | 0 | 0 | 0
|  |  |  | # Component Count (Screens) | -> | 0 | 0 | -- | 0
|  |  |  | Test Case Complexity | -> | Complex (>51) | 14 | -- | --
|  |  |  | AUT | -> | COTS (Commercial) | 1 | 2% | 0
|  |  |  | Architecture | -> | Supported | 1 | 0% | 0
|  |  |  | Tool Object Recognition | -> | Easily recognized | 1 | 10% | 0
|  |  |  | Working Prototype | -> | POC completed | 1 | 5% | 0
|  |  |  | Application Flow | -> | Linear | 1 | 5% | 0
|  |  |  | Framework | -> | TAF ACTION | 6 | 35% | 0
|  |  |  | Data Intensive | -> | Light data input | 2 | 3% | 0
|  |  |  | Viable Test Data Source | -> | Data available | 1 | 5% | 0
|  |  |  | Skill Level | -> | Expert | 1 | 35% | 0
[7 empty] | Sub Total | 100% | 0
Note on G3: The % increase to LOE to account for Lead resource to manage team resources.
Note on G4: Screen or components to automate. Also know as business processes.
Note on G5: The average number of interactions (test steps) per screen. Click, Select, Enter text are examples of application interactions.
Note on G6: Commercial off-shelf application (COTS) known and recognized by the automation tool or custom built application.
Note on G7: The core application language is recognized/understood by the automation tool.
Note on G8: The level of difficulty the automation tool has in recognizing and identifying application objects. Also includes effort to maintain the objects.
Note on G9: Proof of concept (POC) has been completed, proving the automation tool works with the AUT.
Note on G10: The process flow is simple, one-way (like a registration form) is linear. Non-linear is complex choices like Ebay or Amazon where the user could select any button or widget on the screen and the flow is very dynamic.
Note on G11: TAF flavors of automation. Consult TAF Strategy docx for details.
Note on G12: Large data sets or multiple data variations for the same test case is considered "data heavy input". One time use or low data variations is light data input.
Note on G13: Valid and known data is available for input or a reliable contact (Business SME) is providing valid test data.
Note on G14: Automation developer skill level. When in doubt, choose the lower skill level to increase the LOE.
Note on G18: The % increase to LOE to account for Lead resource to manage team resources.
Note on G19: Screen or components to automate. Also know as business processes.
Note on G20: The average number of interactions (test steps) per screen. Click, Select, Enter text are examples of application interactions.
Note on G21: Commercial off-shelf application (COTS) known and recognized by the automation tool or custom built application.
Note on G22: The core application language is recognized/understood by the automation tool.
Note on G23: The level of difficulty the automation tool has in recognizing and identifying application objects. Also includes effort to maintain the objects.
Note on G24: Proof of concept (POC) has been completed, proving the automation tool works with the AUT.
Note on G25: The process flow is simple, one-way (like a registration form) is linear. Non-linear is complex choices like Ebay or Amazon where the user could select any button or widget on the screen and the flow is very dynamic.
Note on G26: TAF flavors of automation. Consult TAF Strategy docx for details.
Note on G27: Large data sets or multiple data variations for the same test case is considered "data heavy input". One time use or low data variations is light data input.
Note on G28: Valid and known data is available for input or a reliable contact (Business SME) is providing valid test data.
Note on G29: Automation developer skill level. When in doubt, choose the lower skill level to increase the LOE.
Note on T32: Component count from the COMPONENTS PLANNED worksheet. The planned count is to ensure that all components that have been PLANNED are included in the estimation model. Note: Entering planned components is encouraged when creating an estimation and will improve accuracy and traceability to the work performed.
Note on U32: Component count from this estimation sheet Cells I4, I19, I34, I49.
Note on G33: The % increase to LOE to account for Lead resource to manage team resources.
Note on G34: Screen or components to automate. Also know as business processes.
Note on G35: The average number of interactions (test steps) per screen. Click, Select, Enter text are examples of application interactions.
Note on G36: Commercial off-shelf application (COTS) known and recognized by the automation tool or custom built application.
Note on G37: The core application language is recognized/understood by the automation tool.
Note on G38: The level of difficulty the automation tool has in recognizing and identifying application objects. Also includes effort to maintain the objects.
Note on G39: Proof of concept (POC) has been completed, proving the automation tool works with the AUT.
Note on G40: The process flow is simple, one-way (like a registration form) is linear. Non-linear is complex choices like Ebay or Amazon where the user could select any button or widget on the screen and the flow is very dynamic.
Note on G41: TAF flavors of automation. Consult TAF Strategy docx for details.
Note on G42: Large data sets or multiple data variations for the same test case is considered "data heavy input". One time use or low data variations is light data input.
Note on U42: Project is based on 40 week. Provide the resource count and estimate the project length.
Note on G43: Valid and known data is available for input or a reliable contact (Business SME) is providing valid test data.
Note on G44: Automation developer skill level. When in doubt, choose the lower skill level to increase the LOE.
Note on G48: The % increase to LOE to account for Lead resource to manage team resources.
Note on G49: Screen or components to automate. Also know as business processes.
Note on G50: The average number of interactions (test steps) per screen. Click, Select, Enter text are examples of application interactions.
Note on G51: Commercial off-shelf application (COTS) known and recognized by the automation tool or custom built application.
Note on G52: The core application language is recognized/understood by the automation tool.
Note on G53: The level of difficulty the automation tool has in recognizing and identifying application objects. Also includes effort to maintain the objects.
Note on G54: Proof of concept (POC) has been completed, proving the automation tool works with the AUT.
Note on G55: The process flow is simple, one-way (like a registration form) is linear. Non-linear is complex choices like Ebay or Amazon where the user could select any button or widget on the screen and the flow is very dynamic.
Note on G56: TAF flavors of automation. Consult TAF Strategy docx for details.
Note on G57: Large data sets or multiple data variations for the same test case is considered "data heavy input". One time use or low data variations is light data input.
Note on G58: Valid and known data is available for input or a reliable contact (Business SME) is providing valid test data.
Note on G59: Automation developer skill level. When in doubt, choose the lower skill level to increase the LOE.

## ROI INTRODUCTION
Introduction
Testing is a costly investment, a necessary evil, and is not a revenue stream. That is why automation is so important to cutting costs.
Automation cost can be controlled by framework design but cost can also be controlled by the resources used to develop, maintain and execute automated tests. This ROI worksheet will reveal the costs involved and will estimate the return on investment (ROI) based on several key factors surrounding the development and execution of automated tests.
These key factors will help technology leaders identify and understand when a positive ROI can be achieved and the true cost of the initial investment in automation. The true investment value is the cost of developing automation minus the benefit of automation in the first year.
Example: If the develoment cost is $300k and the cost savings is $200k then the true cost of the initial financial investment in the first year is $100k, only a fraction of the original investment (in year one). The follwing years ROI will grow faster because development cost has already been absorbed.
On the ROI worksheet, there are inputs for bill rate, testing frequency and the costs associated with investigating test failures as well as when the automation team must update or correct automated tests. This ROI sheet will reveal many of these hidden costs so the ROI is projected with greater accuracy.

## SUMMARY ROI
Automation ROI
ROI Tool for project delivery of fixed time, work and resources
Automation Development
Developmnet LOE | 1730
Hours per Test Case | 1.2348
Cost per Test Case | 39.5146
Cost | 55360
First Year ROI
First Year Manual Testing without Automation | 1022169.6
First Year Testing with Manual and Automation | 486868
535301.6
ROI (Includes Dev cost)
Year 1 | 535301.6
Year 2 | 1369176.8
Year 3 | 2203052
Year 4 | 3036927.2
Year 5 | 3870802.4
Note on C13: Total Manual Cost Estimate: First month is manual cost only. Multiply first month by 12 to calculate the estimated manual cost for the year.
Note on C14: Calculate the estimated manual cost AND automation cost (development and maintenance) to estimate the ROI for the first year.
Note on C15: Cost Savings Cost Savings (also know as cost avoidance) is the money that is "not spent" on manual testing when automation testing is used instead of manual. Comparing the manual cost to automation cost (including script development and maintenance) creates the ROI for year one. Year one is often (but not always) negative. Subsequent years are positive because the development cost was absorbed in year one.

## DETAILED ROI
Development Cost Basis | FTE: 2 | Manual Execution During the Transition | [6 empty] | Automation Execution During the Transition | [5 empty] | Automation Maintenance |  |  |  | Sub Total | Jim Sears
Bill Rate | 32 | 2 | Executions per Release | [5 empty] | 20 | Executions per Release | [9 empty] | 2018-02-14
Test Case Count | 1401 | 0.75 | Execution Time | [5 empty] | 0.01 | Execution Time | [9 empty] | Version 2.1
Development Time (Hours) | 1730 | 2 | Failure Analysis Time | [5 empty] | 0.5 | Failure Analysis Time |  |  |  |  | 5 | Script Maintenance |  |  |  | TAF
Delivery Time (Months) | 6 | 20% | Failure Percentage | [5 empty] | 15% | Failure Percentage |  |  |  |  | 10% | Failure Percentage
|  | 32 | Bill Rate | [5 empty] | 32 | Bill Rate |  |  |  |  | 32 | Bill Rate
Release Month | Development Cost | Test Count | Execution Count | Execution Cost | Failure Count | Analysis Cost | Manual Cost | Effort (Hours) | Test Count | Execution Count | Execution Cost | Failure Count | Analysis Cost | Effort (Hours) | Test Count | Main-tenance Cost | Effort (Hours) |  | Automation Cost | Total Cost | Total Effort (Hours)
July | 9226.6667 | 1401 | 2802 | 67248 | 280.2 | 17932.8 | 85180.8 | 2661.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 94407.4667 | 2661.9
August | 9226.6667 | 1167.5 | 2335 | 56040 | 233.5 | 14944 | 70984 | 2218.25 | 233.5 | 4670 | 1494.4 | 35.025 | 560.4 | 17.5125 | 3.5025 | 560.4 | 17.5125 |  | 2615.2 | 82825.8667 | 2253.275
September | 9226.6667 | 934 | 1868 | 44832 | 186.8 | 11955.2 | 56787.2 | 1774.6 | 467 | 9340 | 2988.8 | 70.05 | 1120.8 | 35.025 | 7.005 | 1120.8 | 35.025 |  | 5230.4 | 71244.2667 | 1844.65
October | 9226.6667 | 700.5 | 1401 | 33624 | 140.1 | 8966.4 | 42590.4 | 1330.95 | 700.5 | 14010 | 4483.2 | 105.075 | 1681.2 | 52.5375 | 10.5075 | 1681.2 | 52.5375 |  | 7845.6 | 59662.6667 | 1436.025
November | 9226.6667 | 467 | 934 | 22416 | 93.4 | 5977.6 | 28393.6 | 887.3 | 934 | 18680 | 5977.6 | 140.1 | 2241.6 | 70.05 | 14.01 | 2241.6 | 70.05 |  | 10460.8 | 48081.0667 | 1027.4
December | 9226.6667 | 233.5 | 467 | 11208 | 46.7 | 2988.8 | 14196.8 | 443.65 | 1167.5 | 23350 | 7472 | 175.125 | 2802 | 87.5625 | 17.5125 | 2802 | 87.5625 |  | 13076 | 36499.4667 | 618.775
January | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401 | 28020 | 8966.4 | 210.15 | 3362.4 | 105.075 | 21.015 | 3362.4 | 105.075 |  | 15691.2 | 15691.2 | 210.15
February | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401 | 28020 | 8966.4 | 210.15 | 3362.4 | 105.075 | 21.015 | 3362.4 | 105.075 |  | 15691.2 | 15691.2 | 210.15
March | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401 | 28020 | 8966.4 | 210.15 | 3362.4 | 105.075 | 21.015 | 3362.4 | 105.075 |  | 15691.2 | 15691.2 | 210.15
April | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401 | 28020 | 8966.4 | 210.15 | 3362.4 | 105.075 | 21.015 | 3362.4 | 105.075 |  | 15691.2 | 15691.2 | 210.15
May | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401 | 28020 | 8966.4 | 210.15 | 3362.4 | 105.075 | 21.015 | 3362.4 | 105.075 |  | 15691.2 | 15691.2 | 210.15
June | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401 | 28020 | 8966.4 | 210.15 | 3362.4 | 105.075 | 21.015 | 3362.4 | 105.075 |  | 15691.2 | 15691.2 | 210.15
| 55360 | [5 empty] | 298132.8 | 9316.65 |  |  |  |  | 28580.4 | 893.1375 |  | 28580.4 | 893.1375 |  | 133375.2 | 486868 | 11102.925
Development Cost
Automation Dev LOE | 1730
Dev Hours per Test Case | 1.2348
Cost per Test Case | 39.5146 | [15 empty] | Code Drop Execution Coverage (Year)
Cost | 55360 | [15 empty] | Manual | Automation
[16 empty] | 33624 | 336240
First Year ROI
First Year Manual Testing without Automation | 1022169.6
First Year Testing with Manual and Automation | 486868
535301.6
ROI
Year 1 | 535301.6
Year 2 | 1369176.8
Year 3 | 2203052
Year 4 | 3036927.2
Year 5 | 3870802.4
Note on C2: FTE: Full Time Employee Nbr of developers required based on 40 hour work week. Caculation based on Dev Hours and Delivery Months.
Note on C3: Automation Bill Rate: Labor cost to develop automation. Average hourly bill rate for on-shore off-shore contractor perm.
Note on E3: Executions per Release Frequency, the number of times the same Test will be executed in a Release. Ideal execution count is once after each code drop but time and resource availability makes that impractical and the reality is that each Test is executed on average 1-2 times per Release manually and then mulitiple times with automation.
Note on M3: Executions per Release The number of times the same Test will be executed in a Release. Ideal execution count is once after each code drop but time and resource availability makes that impractical and the reality is that each Test is executed on average 1-2 times per Release manually and then mulitiple times with automation.
Note on C4: Test Case Count: Total number of Tests that will be executed once during a Release. This number is NOT the number of times(quantity or frequency) a Test is executed. Enter Test Names or dummy values like T1, T2, T3 on the TESTS sheet and the test count will be calculated automatically.
Note on E4: Test Execution Time Average time to execute a single test case.
Note on M4: Test Execution Time Average time to execute a single test case.
Note on C5: Estimate total number of hours to automate the Test Case Count. Known as LOE (Level of Effort), this value is automatically retrieved from the ESTIMATION sheet.
Note on E5: Test Failure Analysis The amount of time spent investigating failures WHEN a failure occurs. Root cause could be data, application defect or environment but the analysis cost is tracked separate from execution cost.
Note on M5: Test Failure Analysis The amount of time spent investigating failures WHEN a failure occurs. Root cause could be data, application defect or environment but the analysis cost is tracked separate from execution cost.
Note on T5: Automation Script Maintenance Cost LOE to update or correct scripts broken due to application changes or script failure. Not all failures are automation related or require automation effort to correct.
Note on C6: Number of months to deliver automation. This is the desired time frame to transistion from manual testing to automated testing for the given test case count. Please enter a value between 1-11. 12 will invalidate the results for automation maintenance.
Note on E6: Test Case Failure: Test execution requires investigation when a Test fails.(manual or automated). This percentage represents the average number of tests in a release that fail and require investigation.
Note on M6: Test Case Failure: Test execution requires investigation when a Test fails.(manual or automated). This percentage represents the average number of tests in a release that fail and require investigation.
Note on T6: Test Case Failure: Test execution requires investigation when a Test fails.(manual or automated). This percentage represents the average number of tests in a release that fail and require corrective action by the automation team. This is a subset of the the failures from the failure analysis. It is a subset because not all test case failures root cause is because the application changed and the script needs updating. Sometimes it is data or environment related.
Note on E7: Manual Execution Cost Labor cost to execute a test case manually and analyze test case failures. Average hourly bill rate for on-shore off-shore contractor perm.
Note on M7: Automation Execution Cost Labor cost to execute an automated test case and analyze test case failures. Average hourly bill rate for on-shore off-shore contractor perm.
Note on T7: Automation Maintenance Cost Labor cost to correct or enhance existing automation scripts or tests when the application changes. Does not account for new test case development or new application features. Maintenance only. Average hourly bill rate for on-shore off-shore contractor perm.
Note on Z9: Total Cost: Total cost of Manual and Automated Test execution.
Note on AA9: Total Hours: Total hours manual and automation.
Note on B10: Select starting month for analysis. This is the month automation development begins.
Note on J10: Basis for calculating cost of one year of manual testing.
Note on Z21: Basis for calculating cost of one year of automated testing.
Note on C31: Current automation cost for one year. No automation testing.
Note on C32: Cost of Manual and automated testing for year one. (U21)
Note on C33: Cost Savings Cost Savings is the comparison of manual Testing for one year versus the cost of Testing using automation as it is developed over the course of first year. The faster the automation is developed the greater the cost savings. (Adjust the Automation Dev Time to a lower number will yield greater cost savings.) (C6)

## TESTS
TEST NAME | DESCRIPTION
TEST_0001
TEST_0002
TEST_0003
TEST_0004
TEST_0005
TEST_0006
TEST_0007
TEST_0008
TEST_0009
TEST_0010
TEST_0011
TEST_0012
TEST_0013
TEST_0014
TEST_0015
TEST_0016
TEST_0017
TEST_0018
TEST_0019
TEST_0020
TEST_0021
TEST_0022
TEST_0023
TEST_0024
TEST_0025
TEST_0026
TEST_0027
TEST_0028
TEST_0029
TEST_0030
TEST_0031
TEST_0032
TEST_0033
TEST_0034
TEST_0035
TEST_0036
TEST_0037
TEST_0038
TEST_0039
TEST_0040
TEST_0041
TEST_0042
TEST_0043
TEST_0044
TEST_0045
TEST_0046
TEST_0047
TEST_0048
TEST_0049
TEST_0050
TEST_0051
TEST_0052
TEST_0053
TEST_0054
TEST_0055
TEST_0056
TEST_0057
TEST_0058
TEST_0059
TEST_0060
TEST_0061
TEST_0062
TEST_0063
TEST_0064
TEST_0065
TEST_0066
TEST_0067
TEST_0068
TEST_0069
TEST_0070
TEST_0071
TEST_0072
TEST_0073
TEST_0074
TEST_0075
TEST_0076
TEST_0077
TEST_0078
TEST_0079
TEST_0080
TEST_0081
TEST_0082
TEST_0083
TEST_0084
TEST_0085
TEST_0086
TEST_0087
TEST_0088
TEST_0089
TEST_0090
TEST_0091
TEST_0092
TEST_0093
TEST_0094
TEST_0095
TEST_0096
TEST_0097
TEST_0098
TEST_0099
TEST_0100
TEST_0101
TEST_0102
TEST_0103
TEST_0104
TEST_0105
TEST_0106
TEST_0107
TEST_0108
TEST_0109
TEST_0110
TEST_0111
TEST_0112
TEST_0113
TEST_0114
TEST_0115
TEST_0116
TEST_0117
TEST_0118
TEST_0119
TEST_0120
TEST_0121
TEST_0122
TEST_0123
TEST_0124
TEST_0125
TEST_0126
TEST_0127
TEST_0128
TEST_0129
TEST_0130
TEST_0131
TEST_0132
TEST_0133
TEST_0134
TEST_0135
TEST_0136
TEST_0137
TEST_0138
TEST_0139
TEST_0140
TEST_0141
TEST_0142
TEST_0143
TEST_0144
TEST_0145
TEST_0146
TEST_0147
TEST_0148
TEST_0149
TEST_0150
TEST_0151
TEST_0152
TEST_0153
TEST_0154
TEST_0155
TEST_0156
TEST_0157
TEST_0158
TEST_0159
TEST_0160
TEST_0161
TEST_0162
TEST_0163
TEST_0164
TEST_0165
TEST_0166
TEST_0167
TEST_0168
TEST_0169
TEST_0170
TEST_0171
TEST_0172
TEST_0173
TEST_0174
TEST_0175
TEST_0176
TEST_0177
TEST_0178
TEST_0179
TEST_0180
TEST_0181
TEST_0182
TEST_0183
TEST_0184
TEST_0185
TEST_0186
TEST_0187
TEST_0188
TEST_0189
TEST_0190
TEST_0191
TEST_0192
TEST_0193
TEST_0194
TEST_0195
TEST_0196
TEST_0197
TEST_0198
TEST_0199
TEST_0200
TEST_0201
TEST_0202
TEST_0203
TEST_0204
TEST_0205
TEST_0206
TEST_0207
TEST_0208
TEST_0209
TEST_0210
TEST_0211
TEST_0212
TEST_0213
TEST_0214
TEST_0215
TEST_0216
TEST_0217
TEST_0218
TEST_0219
TEST_0220
TEST_0221
TEST_0222
TEST_0223
TEST_0224
TEST_0225
TEST_0226
TEST_0227
TEST_0228
TEST_0229
TEST_0230
TEST_0231
TEST_0232
TEST_0233
TEST_0234
TEST_0235
TEST_0236
TEST_0237
TEST_0238
TEST_0239
TEST_0240
TEST_0241
TEST_0242
TEST_0243
TEST_0244
TEST_0245
TEST_0246
TEST_0247
TEST_0248
TEST_0249
TEST_0250
TEST_0251
TEST_0252
TEST_0253
TEST_0254
TEST_0255
TEST_0256
TEST_0257
TEST_0258
TEST_0259
TEST_0260
TEST_0261
TEST_0262
TEST_0263
TEST_0264
TEST_0265
TEST_0266
TEST_0267
TEST_0268
TEST_0269
TEST_0270
TEST_0271
TEST_0272
TEST_0273
TEST_0274
TEST_0275
TEST_0276
TEST_0277
TEST_0278
TEST_0279
TEST_0280
TEST_0281
TEST_0282
TEST_0283
TEST_0284
TEST_0285
TEST_0286
TEST_0287
TEST_0288
TEST_0289
TEST_0290
TEST_0291
TEST_0292
TEST_0293
TEST_0294
TEST_0295
TEST_0296
TEST_0297
TEST_0298
TEST_0299
TEST_0300
TEST_0301
TEST_0302
TEST_0303
TEST_0304
TEST_0305
TEST_0306
TEST_0307
TEST_0308
TEST_0309
TEST_0310
TEST_0311
TEST_0312
TEST_0313
TEST_0314
TEST_0315
TEST_0316
TEST_0317
TEST_0318
TEST_0319
TEST_0320
TEST_0321
TEST_0322
TEST_0323
TEST_0324
TEST_0325
TEST_0326
TEST_0327
TEST_0328
TEST_0329
TEST_0330
TEST_0331
TEST_0332
TEST_0333
TEST_0334
TEST_0335
TEST_0336
TEST_0337
TEST_0338
TEST_0339
TEST_0340
TEST_0341
TEST_0342
TEST_0343
TEST_0344
TEST_0345
TEST_0346
TEST_0347
TEST_0348
TEST_0349
TEST_0350
TEST_0351
TEST_0352
TEST_0353
TEST_0354
TEST_0355
TEST_0356
TEST_0357
TEST_0358
TEST_0359
TEST_0360
TEST_0361
TEST_0362
TEST_0363
TEST_0364
TEST_0365
TEST_0366
TEST_0367
TEST_0368
TEST_0369
TEST_0370
TEST_0371
TEST_0372
TEST_0373
TEST_0374
TEST_0375
TEST_0376
TEST_0377
TEST_0378
TEST_0379
TEST_0380
TEST_0381
TEST_0382
TEST_0383
TEST_0384
TEST_0385
TEST_0386
TEST_0387
TEST_0388
TEST_0389
TEST_0390
TEST_0391
TEST_0392
TEST_0393
TEST_0394
TEST_0395
TEST_0396
TEST_0397
TEST_0398
TEST_0399
TEST_0400
TEST_0401
TEST_0402
TEST_0403
TEST_0404
TEST_0405
TEST_0406
TEST_0407
TEST_0408
TEST_0409
TEST_0410
TEST_0411
TEST_0412
TEST_0413
TEST_0414
TEST_0415
TEST_0416
TEST_0417
TEST_0418
TEST_0419
TEST_0420
TEST_0421
TEST_0422
TEST_0423
TEST_0424
TEST_0425
TEST_0426
TEST_0427
TEST_0428
TEST_0429
TEST_0430
TEST_0431
TEST_0432
TEST_0433
TEST_0434
TEST_0435
TEST_0436
TEST_0437
TEST_0438
TEST_0439
TEST_0440
TEST_0441
TEST_0442
TEST_0443
TEST_0444
TEST_0445
TEST_0446
TEST_0447
TEST_0448
TEST_0449
TEST_0450
TEST_0451
TEST_0452
TEST_0453
TEST_0454
TEST_0455
TEST_0456
TEST_0457
TEST_0458
TEST_0459
TEST_0460
TEST_0461
TEST_0462
TEST_0463
TEST_0464
TEST_0465
TEST_0466
TEST_0467
TEST_0468
TEST_0469
TEST_0470
TEST_0471
TEST_0472
TEST_0473
TEST_0474
TEST_0475
TEST_0476
TEST_0477
TEST_0478
TEST_0479
TEST_0480
TEST_0481
TEST_0482
TEST_0483
TEST_0484
TEST_0485
TEST_0486
TEST_0487
TEST_0488
TEST_0489
TEST_0490
TEST_0491
TEST_0492
TEST_0493
TEST_0494
TEST_0495
TEST_0496
TEST_0497
TEST_0498
TEST_0499
TEST_0500
TEST_0501
TEST_0502
TEST_0503
TEST_0504
TEST_0505
TEST_0506
TEST_0507
TEST_0508
TEST_0509
TEST_0510
TEST_0511
TEST_0512
TEST_0513
TEST_0514
TEST_0515
TEST_0516
TEST_0517
TEST_0518
TEST_0519
TEST_0520
TEST_0521
TEST_0522
TEST_0523
TEST_0524
TEST_0525
TEST_0526
TEST_0527
TEST_0528
TEST_0529
TEST_0530
TEST_0531
TEST_0532
TEST_0533
TEST_0534
TEST_0535
TEST_0536
TEST_0537
TEST_0538
TEST_0539
TEST_0540
TEST_0541
TEST_0542
TEST_0543
TEST_0544
TEST_0545
TEST_0546
TEST_0547
TEST_0548
TEST_0549
TEST_0550
TEST_0551
TEST_0552
TEST_0553
TEST_0554
TEST_0555
TEST_0556
TEST_0557
TEST_0558
TEST_0559
TEST_0560
TEST_0561
TEST_0562
TEST_0563
TEST_0564
TEST_0565
TEST_0566
TEST_0567
TEST_0568
TEST_0569
TEST_0570
TEST_0571
TEST_0572
TEST_0573
TEST_0574
TEST_0575
TEST_0576
TEST_0577
TEST_0578
TEST_0579
TEST_0580
TEST_0581
TEST_0582
TEST_0583
TEST_0584
TEST_0585
TEST_0586
TEST_0587
TEST_0588
TEST_0589
TEST_0590
TEST_0591
TEST_0592
TEST_0593
TEST_0594
TEST_0595
TEST_0596
TEST_0597
TEST_0598
TEST_0599
TEST_0600
TEST_0601
TEST_0602
TEST_0603
TEST_0604
TEST_0605
TEST_0606
TEST_0607
TEST_0608
TEST_0609
TEST_0610
TEST_0611
TEST_0612
TEST_0613
TEST_0614
TEST_0615
TEST_0616
TEST_0617
TEST_0618
TEST_0619
TEST_0620
TEST_0621
TEST_0622
TEST_0623
TEST_0624
TEST_0625
TEST_0626
TEST_0627
TEST_0628
TEST_0629
TEST_0630
TEST_0631
TEST_0632
TEST_0633
TEST_0634
TEST_0635
TEST_0636
TEST_0637
TEST_0638
TEST_0639
TEST_0640
TEST_0641
TEST_0642
TEST_0643
TEST_0644
TEST_0645
TEST_0646
TEST_0647
TEST_0648
TEST_0649
TEST_0650
TEST_0651
TEST_0652
TEST_0653
TEST_0654
TEST_0655
TEST_0656
TEST_0657
TEST_0658
TEST_0659
TEST_0660
TEST_0661
TEST_0662
TEST_0663
TEST_0664
TEST_0665
TEST_0666
TEST_0667
TEST_0668
TEST_0669
TEST_0670
TEST_0671
TEST_0672
TEST_0673
TEST_0674
TEST_0675
TEST_0676
TEST_0677
TEST_0678
TEST_0679
TEST_0680
TEST_0681
TEST_0682
TEST_0683
TEST_0684
TEST_0685
TEST_0686
TEST_0687
TEST_0688
TEST_0689
TEST_0690
TEST_0691
TEST_0692
TEST_0693
TEST_0694
TEST_0695
TEST_0696
TEST_0697
TEST_0698
TEST_0699
TEST_0700
TEST_0701
TEST_0702
TEST_0703
TEST_0704
TEST_0705
TEST_0706
TEST_0707
TEST_0708
TEST_0709
TEST_0710
TEST_0711
TEST_0712
TEST_0713
TEST_0714
TEST_0715
TEST_0716
TEST_0717
TEST_0718
TEST_0719
TEST_0720
TEST_0721
TEST_0722
TEST_0723
TEST_0724
TEST_0725
TEST_0726
TEST_0727
TEST_0728
TEST_0729
TEST_0730
TEST_0731
TEST_0732
TEST_0733
TEST_0734
TEST_0735
TEST_0736
TEST_0737
TEST_0738
TEST_0739
TEST_0740
TEST_0741
TEST_0742
TEST_0743
TEST_0744
TEST_0745
TEST_0746
TEST_0747
TEST_0748
TEST_0749
TEST_0750
TEST_0751
TEST_0752
TEST_0753
TEST_0754
TEST_0755
TEST_0756
TEST_0757
TEST_0758
TEST_0759
TEST_0760
TEST_0761
TEST_0762
TEST_0763
TEST_0764
TEST_0765
TEST_0766
TEST_0767
TEST_0768
TEST_0769
TEST_0770
TEST_0771
TEST_0772
TEST_0773
TEST_0774
TEST_0775
TEST_0776
TEST_0777
TEST_0778
TEST_0779
TEST_0780
TEST_0781
TEST_0782
TEST_0783
TEST_0784
TEST_0785
TEST_0786
TEST_0787
TEST_0788
TEST_0789
TEST_0790
TEST_0791
TEST_0792
TEST_0793
TEST_0794
TEST_0795
TEST_0796
TEST_0797
TEST_0798
TEST_0799
TEST_0800
TEST_0801
TEST_0802
TEST_0803
TEST_0804
TEST_0805
TEST_0806
TEST_0807
TEST_0808
TEST_0809
TEST_0810
TEST_0811
TEST_0812
TEST_0813
TEST_0814
TEST_0815
TEST_0816
TEST_0817
TEST_0818
TEST_0819
TEST_0820
TEST_0821
TEST_0822
TEST_0823
TEST_0824
TEST_0825
TEST_0826
TEST_0827
TEST_0828
TEST_0829
TEST_0830
TEST_0831
TEST_0832
TEST_0833
TEST_0834
TEST_0835
TEST_0836
TEST_0837
TEST_0838
TEST_0839
TEST_0840
TEST_0841
TEST_0842
TEST_0843
TEST_0844
TEST_0845
TEST_0846
TEST_0847
TEST_0848
TEST_0849
TEST_0850
TEST_0851
TEST_0852
TEST_0853
TEST_0854
TEST_0855
TEST_0856
TEST_0857
TEST_0858
TEST_0859
TEST_0860
TEST_0861
TEST_0862
TEST_0863
TEST_0864
TEST_0865
TEST_0866
TEST_0867
TEST_0868
TEST_0869
TEST_0870
TEST_0871
TEST_0872
TEST_0873
TEST_0874
TEST_0875
TEST_0876
TEST_0877
TEST_0878
TEST_0879
TEST_0880
TEST_0881
TEST_0882
TEST_0883
TEST_0884
TEST_0885
TEST_0886
TEST_0887
TEST_0888
TEST_0889
TEST_0890
TEST_0891
TEST_0892
TEST_0893
TEST_0894
TEST_0895
TEST_0896
TEST_0897
TEST_0898
TEST_0899
TEST_0900
TEST_0901
TEST_0902
TEST_0903
TEST_0904
TEST_0905
TEST_0906
TEST_0907
TEST_0908
TEST_0909
TEST_0910
TEST_0911
TEST_0912
TEST_0913
TEST_0914
TEST_0915
TEST_0916
TEST_0917
TEST_0918
TEST_0919
TEST_0920
TEST_0921
TEST_0922
TEST_0923
TEST_0924
TEST_0925
TEST_0926
TEST_0927
TEST_0928
TEST_0929
TEST_0930
TEST_0931
TEST_0932
TEST_0933
TEST_0934
TEST_0935
TEST_0936
TEST_0937
TEST_0938
TEST_0939
TEST_0940
TEST_0941
TEST_0942
TEST_0943
TEST_0944
TEST_0945
TEST_0946
TEST_0947
TEST_0948
TEST_0949
TEST_0950
TEST_0951
TEST_0952
TEST_0953
TEST_0954
TEST_0955
TEST_0956
TEST_0957
TEST_0958
TEST_0959
TEST_0960
TEST_0961
TEST_0962
TEST_0963
TEST_0964
TEST_0965
TEST_0966
TEST_0967
TEST_0968
TEST_0969
TEST_0970
TEST_0971
TEST_0972
TEST_0973
TEST_0974
TEST_0975
TEST_0976
TEST_0977
TEST_0978
TEST_0979
TEST_0980
TEST_0981
TEST_0982
TEST_0983
TEST_0984
TEST_0985
TEST_0986
TEST_0987
TEST_0988
TEST_0989
TEST_0990
TEST_0991
TEST_0992
TEST_0993
TEST_0994
TEST_0995
TEST_0996
TEST_0997
TEST_0998
TEST_0999
TEST_1000
TEST_1001
TEST_1002
TEST_1003
TEST_1004
TEST_1005
TEST_1006
TEST_1007
TEST_1008
TEST_1009
TEST_1010
TEST_1011
TEST_1012
TEST_1013
TEST_1014
TEST_1015
TEST_1016
TEST_1017
TEST_1018
TEST_1019
TEST_1020
TEST_1021
TEST_1022
TEST_1023
TEST_1024
TEST_1025
TEST_1026
TEST_1027
TEST_1028
TEST_1029
TEST_1030
TEST_1031
TEST_1032
TEST_1033
TEST_1034
TEST_1035
TEST_1036
TEST_1037
TEST_1038
TEST_1039
TEST_1040
TEST_1041
TEST_1042
TEST_1043
TEST_1044
TEST_1045
TEST_1046
TEST_1047
TEST_1048
TEST_1049
TEST_1050
TEST_1051
TEST_1052
TEST_1053
TEST_1054
TEST_1055
TEST_1056
TEST_1057
TEST_1058
TEST_1059
TEST_1060
TEST_1061
TEST_1062
TEST_1063
TEST_1064
TEST_1065
TEST_1066
TEST_1067
TEST_1068
TEST_1069
TEST_1070
TEST_1071
TEST_1072
TEST_1073
TEST_1074
TEST_1075
TEST_1076
TEST_1077
TEST_1078
TEST_1079
TEST_1080
TEST_1081
TEST_1082
TEST_1083
TEST_1084
TEST_1085
TEST_1086
TEST_1087
TEST_1088
TEST_1089
TEST_1090
TEST_1091
TEST_1092
TEST_1093
TEST_1094
TEST_1095
TEST_1096
TEST_1097
TEST_1098
TEST_1099
TEST_1100
TEST_1101
TEST_1102
TEST_1103
TEST_1104
TEST_1105
TEST_1106
TEST_1107
TEST_1108
TEST_1109
TEST_1110
TEST_1111
TEST_1112
TEST_1113
TEST_1114
TEST_1115
TEST_1116
TEST_1117
TEST_1118
TEST_1119
TEST_1120
TEST_1121
TEST_1122
TEST_1123
TEST_1124
TEST_1125
TEST_1126
TEST_1127
TEST_1128
TEST_1129
TEST_1130
TEST_1131
TEST_1132
TEST_1133
TEST_1134
TEST_1135
TEST_1136
TEST_1137
TEST_1138
TEST_1139
TEST_1140
TEST_1141
TEST_1142
TEST_1143
TEST_1144
TEST_1145
TEST_1146
TEST_1147
TEST_1148
TEST_1149
TEST_1150
TEST_1151
TEST_1152
TEST_1153
TEST_1154
TEST_1155
TEST_1156
TEST_1157
TEST_1158
TEST_1159
TEST_1160
TEST_1161
TEST_1162
TEST_1163
TEST_1164
TEST_1165
TEST_1166
TEST_1167
TEST_1168
TEST_1169
TEST_1170
TEST_1171
TEST_1172
TEST_1173
TEST_1174
TEST_1175
TEST_1176
TEST_1177
TEST_1178
TEST_1179
TEST_1180
TEST_1181
TEST_1182
TEST_1183
TEST_1184
TEST_1185
TEST_1186
TEST_1187
TEST_1188
TEST_1189
TEST_1190
TEST_1191
TEST_1192
TEST_1193
TEST_1194
TEST_1195
TEST_1196
TEST_1197
TEST_1198
TEST_1199
TEST_1200
TEST_1201
TEST_1202
TEST_1203
TEST_1204
TEST_1205
TEST_1206
TEST_1207
TEST_1208
TEST_1209
TEST_1210
TEST_1211
TEST_1212
TEST_1213
TEST_1214
TEST_1215
TEST_1216
TEST_1217
TEST_1218
TEST_1219
TEST_1220
TEST_1221
TEST_1222
TEST_1223
TEST_1224
TEST_1225
TEST_1226
TEST_1227
TEST_1228
TEST_1229
TEST_1230
TEST_1231
TEST_1232
TEST_1233
TEST_1234
TEST_1235
TEST_1236
TEST_1237
TEST_1238
TEST_1239
TEST_1240
TEST_1241
TEST_1242
TEST_1243
TEST_1244
TEST_1245
TEST_1246
TEST_1247
TEST_1248
TEST_1249
TEST_1250
TEST_1251
TEST_1252
TEST_1253
TEST_1254
TEST_1255
TEST_1256
TEST_1257
TEST_1258
TEST_1259
TEST_1260
TEST_1261
TEST_1262
TEST_1263
TEST_1264
TEST_1265
TEST_1266
TEST_1267
TEST_1268
TEST_1269
TEST_1270
TEST_1271
TEST_1272
TEST_1273
TEST_1274
TEST_1275
TEST_1276
TEST_1277
TEST_1278
TEST_1279
TEST_1280
TEST_1281
TEST_1282
TEST_1283
TEST_1284
TEST_1285
TEST_1286
TEST_1287
TEST_1288
TEST_1289
TEST_1290
TEST_1291
TEST_1292
TEST_1293
TEST_1294
TEST_1295
TEST_1296
TEST_1297
TEST_1298
TEST_1299
TEST_1300
TEST_1301
TEST_1302
TEST_1303
TEST_1304
TEST_1305
TEST_1306
TEST_1307
TEST_1308
TEST_1309
TEST_1310
TEST_1311
TEST_1312
TEST_1313
TEST_1314
TEST_1315
TEST_1316
TEST_1317
TEST_1318
TEST_1319
TEST_1320
TEST_1321
TEST_1322
TEST_1323
TEST_1324
TEST_1325
TEST_1326
TEST_1327
TEST_1328
TEST_1329
TEST_1330
TEST_1331
TEST_1332
TEST_1333
TEST_1334
TEST_1335
TEST_1336
TEST_1337
TEST_1338
TEST_1339
TEST_1340
TEST_1341
TEST_1342
TEST_1343
TEST_1344
TEST_1345
TEST_1346
TEST_1347
TEST_1348
TEST_1349
TEST_1350
TEST_1351
TEST_1352
TEST_1353
TEST_1354
TEST_1355
TEST_1356
TEST_1357
TEST_1358
TEST_1359
TEST_1360
TEST_1361
TEST_1362
TEST_1363
TEST_1364
TEST_1365
TEST_1366
TEST_1367
TEST_1368
TEST_1369
TEST_1370
TEST_1371
TEST_1372
TEST_1373
TEST_1374
TEST_1375
TEST_1376
TEST_1377
TEST_1378
TEST_1379
TEST_1380
TEST_1381
TEST_1382
TEST_1383
TEST_1384
TEST_1385
TEST_1386
TEST_1387
TEST_1388
TEST_1389
TEST_1390
TEST_1391
TEST_1392
TEST_1393
TEST_1394
TEST_1395
TEST_1396
TEST_1397
TEST_1398
TEST_1399
TEST_1400
Note on A1: * Insert TABLE ROWS as needed by right clicking on a table and selecting Insert and then clicking Row above or Row below.

## LISTS_VALUES
STATUS | DEVELOPER | TESTER | AUTOMATION_LEAD | * Insert TABLE ROWS as needed by right clicking on a table and selecting Insert and then clicking Row above or Row below.
New | Saranya Baskar | UNASSIGNED | Jim Sears (TFS QA CoE)
In Progress | Palanivel Subbiah | David Bing | Mohamed Ibrahim M Abdul Kader
Complete |  | Jeff Williams
Archived

## QUESTIONNAIRE
When Does Test Automation Make Sense? | Response
Does the application expect to have on-going software changes every month? | High
Does the application require testing with large data sets or data variations such as "Registration in all 50 states"? | High
Does the application support many platforms (IE/CHROME/FF or iPhone/Android phones) and the same test needs to be executed on those platforms? | High
Does the application require frequent regression testing iterations or multiple code drops per release? | High
Does the application experience issues with developers code merge or developers overwritting existing code with old code? | High
Does the application need to simulate large number of users who are using the application resources including application rendering time? (this is different than Performance) | High
Is the application user interface comparatively stable and not brand new? | High
Does the application perform need Build Verification (BV) testing for CI/CD or before releasing to the manual team? | High
Is the application functionality critical to business success or business revenue? | High
Does the application have agile SDLC with short sprints with high demand for fast test execution? | High
100%

## HELP
Planning
Add Components (i.e. Business Processes) names to COMPONENTS PLANNED sheet that are required to automate the application test cases.
Give the components meaningful names if possible or use generic names for pre-planning and estimation.
Give each component a step count to reflect the complexity of the step. Complicated components will have higher step counts.
Based on the step count, each component will belong to a group. (Low, Medium, High, Complex)
Assign the component if name is known or assign name when development begins.
Add test names to TESTS sheet.
Again, use generic names for pre-planning if actual test names are not known.
Generic names can be T1, T2, T3. Use Excels drag feature to easily add large number of "T" test cases.
Other columns are optional.
Estimation
Review the ESTIMATION INTRODUCTION sheet for details on the estimation process.
Component groups Low, Medium, High and Complex and represented a Part A, Part B, Part C and Part D. Multiple Parts are used for flexibility.
Each Part could have different circumstances such as Skill Level or Manager Supervision so that is why estimation has 4 Parts. Not All Parts have to be populated.
But there must be a Part populated where a group has components.
1) Enter the details regarding the automation of the application under test.
2) Ensure that the number entered for the # Component Count (Screens) matches the COMPONENTS PLANNED number.
3) Enter the Resource Count for the Project
4) Review the Estimation LOE and adjust the Inputs as needed. Repease as needed.
NOTE Common sense and experience can guide the Test Lead to build a reasonable LOE.
Details
The remaining inputs are for the manual test execution, automated test execution and script maintenance. These inputs also have their own associated wage costs.
| 1) Enter the Development Bill Rate. Enter a blended rate if resources are |  |  | 2) Set the Project start month
on-shore, off-shore or near-shore or if bill-rates differ for the project resources.
3) Enter the Project length
4) Enter the manual test execution effort.
Hover over the cells to see the comments for furth explanation.
5) Enter the test execution automation effort. The execution time is expected to be zero unless data prep must be done prior to every test run.
Ideally, the automated tests will be constructed in such a way that the test data can be generated during the test run or can retrieved from a data source using SQL.
Hover over the cells to see the comments for furth explanation.
6) Enter the script mainentance cost. The script mainteance should ideally be 1 hour
but application complexity or poor environment conditions can impact this number.
Hover over the cells to see the comments for furth explanation.
Failure Percentage is a percentage of a percentage.
During Automated Test Execution, the failures can be related to data, environment, etc.
Of those failures, 10% are related to script maintenance.
ROI
Ideal ROI should have a small savings in the first year; "Year 1".

## VERSION HISTORY
DATE | COMMENTS
2018-03-28 16:00 | Added HELP sheet tab to guide user in entering data to calculate ROI
2018-03-28 16:00 | Added QUESTIONNAIRE sheet tab to guide user/test lead in assessing if application is a candidate for automation.
2018-03-28 16:00 | Modified Input parameter for Test Case Count to automatically calculate the value by counting Test Names on the TESTS sheet tab.